Table of Contents

# MSCAST ERP: Options Assessment & Phased Build Plan

Version: 2.0 · Date: 21 September 2026 · Prepared for: Sanjay (the implementer) · Status: planning record, written 16 Sep 2026 before the POC was built. §1–4 (platform choice), §8 (cost) and §11 (risks) stand. §5–7, §9 and §10 are the plan as written; the build has overtaken parts of them (see below).

## Current state vs this plan

- What exists today: read doc 03 (Requirements Traceability) and the POC README (POC README), not this document.

- Instances: Live POC https://mscast.carobar.net (MSCAST staff, own logins); DEV https://mscastdev.carobar.net (demos, screenshots, development).

- Built (§6 lists as P0 work): app mscast_erp with every doctype, report, print format, workflow and control, fixtures exported; release v0.9.0; image mscast/erpnext:v16-app; ERPNext/Frappe v16.

- Code ownership (open): repo is github.com/cb1-tech/mscast (owner-held), not MSCAST’s own. §3 cites “custom app in MSCAST’s own Git repository” as a reason for self-build. Transfer or mirror to MSCAST: not decided.

- AI layer (differs from §7): the AI-written briefing, emailed 08:35 IST (to waseemraj@mcast.co.in on Live POC), runs through a local model router, not Gemini on Vertex AI. A 16-rule exception sweep runs at 06:00 with no model. No per-document cost; no Google Cloud project.

- BRM control (built): no certified BRM = no supplier payment, on Payment Entry and Journal Entry, for every user. Per-supplier “Exempt from BRM certification” flag for utilities, rent, statutory. A BRM cannot be certified until its four checks (qty, rate, inspection, delivery) are ticked. Differs from §6: a director can create, certify and mark paid a BRM alone; MSCAST to confirm (Q21, doc 03).

- PO control (built): a PO cannot be approved unless someone with Purchase User sent it.

- Decisions: D5 answered by the build; D4 is MSCAST’s own decision; D1 decided in doc 08 (§10).

- Engagement: unpaid; the implementer builds this for MSCAST as a family friend and is not competing with ERPens. §3 and §8 compare options only.

Inputs: MSCAST “ERP_Requirement_Final” (PDF, 15 pages, incl. Accounts POV), mapped in doc 03 (97 requirements) · ERPens “Revised Proposal – Mscast” (PDF) · MSCAST Knowledge Base (public research) · doc 02 Research Appendix (open-source ERPs, Frappe apps, alternative strategies, Gemini automation).

Assumptions (confirmed by Sanjay, 16 Sep 2026): up to 10 ERP users · current tools Tally Prime, Excel/Google Sheets, paper/WhatsApp · phased self-build · greenfield: no existing server or software reused; only existing assets are the domain and Google Workspace.

## 1. Executive summary

- Recommendation: ERPNext v16 + India Compliance + Frappe HR, phased self-build, six staggered phases, Oct 2026 – Jul 2027 (§6). Operations first (engineering, projects, procurement, stock, dispatch). Accounts leave Tally on 1 Apr 2027 (financial-year start). AI track in parallel (§7).

- The ERPens proposal is already open source: it is ERPNext (GPL-3, 38.6k GitHub stars, v16.35.0 released 15 Sep 2026). ₹3.6 L + GST buys configuration and customisation, not software. The real choice: who builds, which version, which scope, who owns the code.

- Why ERPNext (of ~25 alternatives, §4): only fully open-source option covering India GST, e-way bill, e-invoice, GSTR-1/2B reconciliation, TDS and Indian payroll without per-user licences; already handles most ETO project, procurement, subcontracting and quality flows. Runners-up: Odoo Enterprise (≈₹1,150/user/month, Custom plan, secondary source), Zoho One (weak ETO), Tally + InvenTree + OpenProject (cheap, data silos).

- Coverage of 97 requirements (doc 03): ~half standard ERPNext v16 / India Compliance / Frappe HR; ~a quarter configuration; 22 custom; 1 integration (biometric access control); 3 need clarification or the CA. PF/ESI/PT/TDS payroll is in scope.

- ERPens proposal (implementer’s reading): 31 requirements absent, 18 partial; ~half its “custom development” lines are standard v16 configuration (§3).

- 3-year cash (§8): self-build ≈₹2.5–4.5 L + implementer’s time; ERPens ≈₹7.8 L without support plan, ≈₹12.5–14 L with it. Each figure labelled estimate or verified price.

## 2. MSCAST in brief

From MSCAST’s requirement document: - Business: engineering consultancy for the steel industry (design & drawing, consultancy, spares supply, equipment supply). Manufacturing is outsourced. - Departments: Sales, Projects (project coordinator sits in Accounts), Engineering, Procurement, Accounts & Finance, Erection & Commissioning, Spares. - Internal documents: PCC sheet · MDF (Material Data File / material list) · bought-out list · techno-commercial comparison · MDM (Material Dispatch Memo) with Annexure-I free-issue list · DI (Delivery Instruction; suppliers ship direct to customer site) · BRM certifying supplier bills · PBG · proforma and retention supplementary invoices · commissioning / preliminary / final certificates. - Accounts today: Tally; monthly project-cost MIS, BS, P&L, cash flow. - Accounts wants: MCA audit trail with auditor login · alerts · daily SMS summary to COO/CFO · 8-year retention · Schedule III-style registers (MSME payables, fixed assets and CWIP, inventory and WIP, GSTR reconciliations, payroll reconciliation).

From public research (confirm in discovery): - MSCAST Engineering Pvt Ltd, Pune; CIN U74900PN2010PTC137644; incorporated 29 Oct 2010; GSTIN 27AAGCM8444B1ZI; up to 10 people; declared turnover ₹1–2 Cr; GST turnover band ₹1.5–5 Cr. - Offer: continuous casting machines (CCMs) and CCM equipment for steel billets, aluminium billet casting machines, pouring casting machines, conveyors; engineering services (layouts, P&IDs, hydraulic circuits, erection supervision). - Model (inferred): design-led engineer-to-order projects, fabrication probably outsourced (job work); few large orders (₹11 L – ₹2 Cr per machine, market prices); deep multi-level BOMs; many bought-outs; dispatch in lots; erection and commissioning; retention; bank guarantees. - Online: two free IndiaMART listings, one TradeIndia listing, placeholder website. Digital lead generation is a separate opportunity.

ERP implication: project-centric (Sales Order = Project = cost centre). Key reports: project P&L (estimate vs actual), cash-flow forecast, BG/retention/LD exposure. Low volume: a small server is enough.

## 3. What the ERPens proposal contains

| Proposal item | In ERPNext v16 | Class | Coverage · remaining effort |
| --- | --- | --- | --- |
| CRM, Sales, Procurement, Inventory, Accounts, GST/TDS, Projects, HR/Payroll, Assets, roles, workflows | Standard modules + India Compliance + Frappe HR | Config | Full · config |
| Drawing upload & revision control | Not built in (attachments + version log of field changes only; no open-source Frappe PLM app found); custom Drawing form, revision history, Draft → Released → Superseded workflow | Custom (mostly no-code) | None · medium, no-code |
| ECR/ECN (not in proposal) | Workflow + BOM Update Tool + BOM Creator | Custom | Partial · low–medium |
| Engineering documentation forms (“MDF”) | Custom forms + print formats (proposal does not define “MDF”) | Custom (no-code) | Framework · low |
| Bought-out item tracking | Item groups, Material Request from BOM, Procurement Tracker, Project-wise Stock Tracking | Config | Mostly full · low |
| Engineering approvals | Workflow | Config | Full · config |
| Activity & man-hours, engineering cost allocation | Timesheet, Activity Type/Cost → Project costing; cost centres/dimensions | Config | Full / mostly full · config–low |
| Project kick-off workflow | Project Template + Workflow | Config | Full · config |
| Dispatch schedule | Sales Order line delivery dates, milestones + custom report | Light custom | Partial · low |
| Completion certificate | New form + print format | Custom (no-code) | None · low |
| Retention tracking | Not in ERPNext or India Compliance (“retention” in code = stock samples); payment terms + custom fields + report; automatic retention ledger entries need code | Custom | Workaround · low–medium |
| Supplier coordination, project docs | Supplier portal, comments, assignments, Google Drive attachments | Config | Partial · low |
| Techno-commercial comparison | Built-in “Supplier Quotation Comparison” is price only; technical scoring to add | Custom (light) | Partial · low–medium |
| MDM, delivery instructions | Delivery Note / Shipment / e-way bill + custom fields + print formats | Light custom | Partial · low |
| Free-issue material | Subcontracting Order “Supplied Items”, Customer Provided Items, v16 Subcontracting Inward Order; India Compliance job-work GST challans | Config | Full · config |
| Inspection planning | Quality Inspection Template, Quality Procedure/Goal/Review/NC exist; plan/calendar is custom | Partly custom | Partial · low–medium |
| Supplier performance | Supplier Scorecard | Config | Full · config |

Genuinely custom: drawing register with revision control; ECR/ECN; techno-commercial (technical + price) comparison; retention money; completion certificates; dispatch memo and schedule; BG and LD registers; inspection plan. Mostly no-code (custom forms/fields, workflows, print formats), packaged in a custom app. Python code is needed only for: automatic retention accounting postings; automatic BOM/work-order replacement from an ECN; CAD/PDM integration; custom web portals; changes to core document behaviour.

In MSCAST’s document, missing from the proposal (doc 03, “In ERPens proposal” = No): PCC sheet and PO-vs-PCC control; BRM; project MIS template and closure reports; SO↔PO↔invoice tracker; proforma invoice; additional claims; spares handover; MCA audit trail with auditor login; incomplete-data alerts; daily COO/CFO summary; 8-year retention and India data residency; MSME payables; gratuity, deferred tax, customer-owned (Tata Motors) assets; CWIP; project WIP valuation; biometric access-control attendance; cheque printing; prior-period and penalty accounts; warranty claims.

Also missing (business analysis): BG/LC register with expiry alerts; LD tracking; milestone billing / payment schedules; cost-estimation sheet per machine family; ECR/ECN; partial BOM release; e-way bill scope and India Compliance API credits; export documents, multi-currency; warranty, spares, service visits; data-migration volumes; ERPNext version (must be v16); code ownership (custom app in MSCAST’s own Git repo); handover and exit terms.

Cost and rollout observations: AWS at ₹10k/month is high for ≤10 users (Frappe Cloud Mumbai or a small India VPS ≈ half). The 12–14 week “big bang” rollout gives the whole business one go-live. No accounting cut-over timing against the financial year.

## 4. Options assessed (details in doc 02)

Scores 1–5, higher is better (cost: higher = cheaper; lock-in: higher = less lock-in).

| Strategy | India compliance | ETO fit | Cost | Time-to-value | Maintainability | Lock-in | Google Workspace fit | AI readiness | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ERPNext v16 + India Compliance (recommended) | 5 | 4 | 4 | 4 | 3 | 5 | 3 | 3 | 31 |
| Odoo 19 Enterprise (Custom plan) | 5 | 4 | 2 | 4 | 4 | 2 | 3 | 4 | 28 |
| Zoho One / Zoho apps (SaaS) | 5 | 2 | 3 | 5 | 5 | 1 | 3 | 4 | 28 |
| Low-code (AppSheet/NocoDB) + Tally | 2 | 3 | 4 | 4 | 2 | 3 | 5 | 3 | 26 |
| Odoo 19 Community + OCA | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 2 | 24 |
| Best-of-breed OSS (InvenTree + OpenProject + Mayan) + Tally | 4 | 4 | 3 | 2 | 2 | 4 | 2 | 3 | 24 |
| Custom build (e.g. Next.js/Postgres) | 1 | 5 | 1 | 1 | 2 | 3 | 4 | 5 | 22 |
| SAP Business One | 5 | 3 | 1 | 3 | 4 | 1 | 2 | 3 | 22 |
| Carbon (crbnos) | 1 | 3 | 3 | 2 | 2 | 3 | 2 | 4 | 20 |
| Dolibarr / Tryton / iDempiere / Axelor / metasfresh / OFBiz | 1–2 | 2–4 | 3–4 | 2 | 2 | 4 | 1–2 | 1–2 | ≤20 |

Also checked: AureusERP, qcadoo, Appsmith, Budibase.

Why others fell short: - Odoo Community: GSTR filing (l10n_in_reports), Indian payroll, PLM, Quality, full accounting reports are Enterprise-only; OCA l10n-india is empty. - Carbon: licence restricts internal production use unless changes are open-sourced; no GST. - Custom build: rebuilds what ERPNext solves; GST, payroll, audit-trail compliance risk. - Tally-centred stacks: no single project P&L.

Compliance facts: - Since 1 Apr 2023 every Pvt Ltd company must keep books in software with an audit trail that cannot be switched off. Rules out spreadsheets and low-code for accounting. - E-invoicing mandatory above ₹5 Cr AATO; MSCAST is near that band; CA to confirm. - E-way bills apply to machine dispatches.

## 5. Target solution (as planned)

| Layer | Plan |
| --- | --- |
| ERP core | ERPNext v16 (not v15) at erp.<mscast-domain>; frappe/india-payroll works only on v16 |
| India compliance | India Compliance (resilient-tech, GPL-3, v16.9.0): GST, e-way bill, e-invoice, GSTR-1 (books vs filed), 2A/2B reconciliation, MCA audit trail (cannot be disabled once on; switch on at site creation), Schedule III BS/P&L templates. API calls use paid credits (500 free trial): get a quote |
| HR | Frappe HR (v16.18.1): employees, leave, attendance, site expense claims. Payroll: D3 |
| Custom app | mscast_erp in a private GitHub repo owned by MSCAST; forms, custom fields, workflows, print formats exported as fixtures (version-controlled, portable) |
| Sites | Staging (UAT) + Production; offsite_backups → Google Drive / S3 |
| Hosting (D1) | Must be in India: Companies (Accounts) Rules 2014, Rule 3(5) (amended 2022): daily backups of electronic books on servers in India. A: Frappe Cloud Mumbai (server and offsite backups in ap-south-1); site plans $25–38/month (₹2,050–3,075) Standard/Professional; custom apps need a private bench group (from $25/month); expect ≈$50–65/month (≈₹4–5.5k), confirm at sign-up; managed upgrades and backups. B: self-managed India VPS (e.g. DigitalOcean Bangalore, General Purpose 2 vCPU/8 GB, $63/month) with frappe_docker + a small staging droplet. Plan recommended A (least ops for a remote one-person team); ERPNext is GPL and backups restore anywhere. Current decision: §10 |
| Identity | Google Sign-In (built-in Social Login Key), restricted to the company domain; offboarding in Workspace |
| Documents | Shared Drive per project for drawings and files; ERPNext Drawing Register holds number, revision, status, approval, Drive link |
| Email / calendar | Gmail account in ERPNext; Google Calendar sync (built-in) |
| Reporting | ERPNext reports and dashboards; Frappe Insights later if needed |
| Automation / AI | Apps Script + Gemini on Vertex AI (asia-south1, Mumbai) to start, no new server; n8n in Docker above ~5 flows. ERPNext REST API via a draft-only user; webhooks signed with HMAC; alerts/digests to Gmail and Chat (§7) |
| Mobile / site | ERPNext responsive web + Frappe HR mobile (attendance, expenses) |
| Tally Prime | Books of account until 31 Mar 2027, then read-only for the FY 2026-27 audit |

## 6. Phased, staggered roadmap (as planned)

Rules: - Each phase goes live alone and is used for real before the next starts; one department cuts over at a time; the previous phase stable ≥2 weeks. - Tally stays the book of record until the year-end cut-over. - Each phase ends at a go/no-go gate: named MSCAST users sign off UAT on staging. One named MSCAST key user per phase owns UAT and trains colleagues. - Build and test on staging first. Production changes ship via the Git repo, never by editing production. - Remote delivery: MSCAST is in Pune; the implementer is remote. Budget (a) scheduled video UAT sessions, (b) optionally a Pune ERPNext freelancer/partner for on-site training and the P4 accounts cut-over. - #n below = backlog item in §9.

| Phase | Window (indicative) | Goes live for | Gate |
| --- | --- | --- | --- |
| P0 Discovery & foundations | 21 Sep – 16 Oct 2026 (4 wks) | Nobody yet | G0: scope, hosting, CA alignment |
| P1 Sales, PCC, projects & engineering core | 19 Oct – 4 Dec 2026 (7 wks) | Sales, projects, engineering | G1 |
| P2 Procurement, PCC control, BRM, stock, subcontracting, quality | 7 Dec 2026 – 29 Jan 2027 (8 wks incl. holidays) | Procurement, stores, QC | G2 (incl. D6 WIP method) |
| P3 MDM/DI dispatch, commercial controls + accounts dry-run | 1 Feb – 26 Mar 2027 (8 wks) | Project coordinator, procurement, accounts (trial) | G3: accounts cut-over go/no-go |
| P4 Accounts, GST, assets & MIS go-live | 1 Apr – 28 May 2027 (8 wks) | Accounts / CA / auditor / management | G4 |
| P5 HR, payroll, biometric attendance, after-sales | 1 Jun – 30 Jul 2027 (9 wks, 2 parallel payroll cycles) | All staff | G5: project close-out |
| AI track A1–A7 | Nov 2026 → mid 2027, parallel | §7 | Pilot gate per flow |

### P0: Discovery & foundations (3–4 weeks)

- Discovery workshop (15-question agenda, KB 00-index.md): machine families, standard designs, BOM depth, in-house vs outsourced, commercial terms (advance, retention, BG, LD), lead sources, meaning of “MDF”, data to migrate.

- Process maps (as-is → to-be): enquiry → quotation → order → engineering → procurement → job work → inspection → dispatch → erection → retention release.

- CA session: e-invoice applicability (AATO); HSN/SAC for complete machines vs services; job-work ITC-04; Tally → ERPNext cut-over 1 Apr 2027 (D2); audit trail; WIP method (D6); SMC / small-company status and cash flow statement; gratuity valuation; MSME disclosures; 8-year archival policy in place of a vendor undertaking.

- Collect formats: PCC, Project MIS, BRM, MDM, DI, Annexure-I, certificates, claims, proforma and supplementary invoices.

- Answer the 19 open questions (doc 03), e.g. “Finance Scaling Management”, biometric device model, Tata Motors assets, GST on closing inventory, WIP method, AS vs Ind AS.

- Foundations: decide hosting (D1); provision production + staging; enable the India Compliance audit trail at site creation; erp.<domain> DNS and SSL; Google Sign-In; Shared Drive structure; private Git repo + mscast_erp scaffold (done; ownership open); naming conventions (projects, items <Project>-<Assy>-<DrgNo>-<Rev>, drawings); user roles.

- Master-data templates: customers; suppliers (capability tags, approved makes); item groups (machines, assemblies, fabricated, bought-outs by category, raw material, spares, services); UOMs (Nos, Set, Kg, m, Manhour, Manday, Lot).

- Exit (G0): signed scope and backlog; hosting live; CA agrees the accounting approach; data owners named.

### P1: Sales, PCC, projects & engineering core (≈7 weeks)

- PCC sheet (#17); kick-off handover (#1); client schedules: project execution, delivery and billing schedules as print formats, periodic project status report to the client.

- MDF: material list per project/assembly from final drawings + bought-out list → Material Requests.

- CRM: Lead → Opportunity → Quotation with versions; lead source tags (IndiaMART, TradeIndia, referral, exhibition); technical questionnaire (#3); cost-estimate sheet (#2).

- Sales Order → Project from template (#1). Timesheets and equipment-wise man-hours (#21).

- Drawing Register (#4), ECR/ECN (#5), engineering doc forms (#6).

- Engineering BOMs per project (multi-level, partial release of long-lead items); template BOMs for standard assemblies.

- Migration: open projects, customers, key suppliers, item catalogue (bought-outs first).

- Exit (G1): all live projects in ERPNext with tasks, drawings and hours logged for 2+ weeks; project status meeting runs from ERPNext, not Excel.

### P2: Procurement, PCC control, BRM, stock, subcontracting & quality (≈8 weeks)

- PO vs PCC control (#17); BRM as a register (#18); drawing/MDF transmittal to equipment manufacturers; vendor free-issue stock declarations, project-wise; supplier MSME/Udyam fields (#22); major-value PO alerts to management (D7).

- D6 decided with the CA (affects warehouse and account setup).

- Purchasing: Material Request from BOM → RFQ (supplier portal / email) → Supplier Quotation → techno-commercial comparison (#7) → approval workflow → PO.

- Stock: purchase receipts, stock entries, project-wise stock. Perpetual inventory off until P4 (no accounting postings while Tally is the book of record).

- Subcontracting / job work: Subcontracting Order with supplied (free-issue) items; vendor-wise balance; subcontracting receipt; GST job-work challans (India Compliance) → ITC-04 data (#9).

- Quality: Quality Inspection Templates per item group; inspection plan (#8); pre-dispatch inspection as a mandatory gate. Supplier Scorecard: on-time delivery, rejection %.

- Exit (G2): every PO for new projects raised in ERPNext; free-issue balances reconcile with vendors; inspection records attached.

### P3: MDM/DI dispatch & commercial controls, plus accounts dry-run (≈8 weeks)

- Dispatch (#10): MDM → DI to supplier with Annexure-I; billing & despatch schedule; contractual delivery schedule vs actual; e-way bill via India Compliance.

- Proforma invoice for advances and scheduled supply; additional client claims; Commissioning / Preliminary / Final certificates (#20); PBG register (#12).

- Erection & commissioning: site tasks, timesheets, expense claims.

- Commercial: payment-terms templates (advance / against dispatch / commissioning); milestone billing plan; retention tracker (#11); BG/LC register, LD exposure (#12); completion certificate (#13).

- Accounts dry-run (Feb–Mar 2027):

  - Chart of accounts, tax templates, TDS categories on staging.

  - Test opening balances from Tally (e.g. 31 Dec 2026).

  - One month of invoices in parallel on staging.

  - CA reviews GSTR-1 and 2B reconciliation outputs.

  - Load fixed-asset register (Companies Act and Income Tax finance books, CWIP, intangibles, customer-owned asset register) and MSME supplier data for opening balances.

  - Configure Auditor (read-only, held by the external CA) and MSCAST Director (approving: PCC, PO, BRM certification, kick-off).

- Exit (G3): dispatches and e-way bills from ERPNext; CA signs off the dry-run → go/no-go for 1 Apr 2027.

### P4: Accounts & GST go-live (from 1 Apr 2027)

- Opening balances at 31 Mar 2027: provisional on day 1, final after Tally year-end close; customer/supplier open items, retention receivables, advances, stock, assets, bank.

- Live: sales invoices (e-invoice if applicable), purchase invoices, payments, bank reconciliation, TDS, GSTR-1 export, 2A/2B reconciliation; perpetual inventory on.

- Reports: project P&L and cash-flow forecast (#14); monthly MIS of project costs, PCC vs actual, SO↔PO↔invoice tracker, project completion closure report (#19).

- Books and controls: BRM gates project payments (#18); cheque printing, petty cash, supplementary (retention) invoices; Schedule III BS/P&L; expense last-year comparison and ratio to sales; TDS on expenses; separate accounts for prior-period items and fines/penalties; MSME 45-day dues report (Form I, Schedule III, s.43B(h)) (#22); fixed assets with depreciation.

- Daily management summary (D7, #24); incomplete-data alerts; auditor login (#23).

- 8-year archival SOP: yearly dumps + year-end exports.

- Tally: read-only for the FY 2026-27 audit; keep TSS until the audit closes.

- Fallback if D2 = keep Tally: ERPNext stays the operations system; monthly voucher export to Tally via XML/JSON; project P&L partial.

- Exit (G4): first monthly close and GST return filed from ERPNext.

### P5: HR, payroll, biometric attendance, after-sales (≈9 weeks)

- HR: employees, attendance (mobile), leave, site-travel expense claims booked to projects.

- Payroll (D3): PF, ESI, PT, TDS with salary slips. Frappe HR + india-payroll in parallel with current payroll for June and July 2027, then live. Before go-live, verify the Maharashtra PT women-exemption fix (₹25,000 threshold) is in the v16 release; v16.0.4 code uses ₹10,000. Reconciliation: Salary Register; PF/ESI/PT/TDS registers.

- Gratuity: payouts in Frappe HR; liability valued by an external/rational method, booked by journal entry.

- Biometric (#27): device punches → Employee Checkin → Shift auto-attendance. ZKTeco/eSSL via LAN sync tool or ADMS push; Matrix COSEC via a small connector. Door locking stays in the access-control system.

- Assets: tools and instruments with calibration (register is in P4).

- After-sales (#15): closure handover to Spares Dept (installed-machine record); serial number per machine/strand; warranty claims; maintenance visits; spares sales orders; AMC.

- Close-out: admin runbook, backup restore test, user guide (short videos), handover.

## 7. Gemini automation track (as planned; built differently, see top)

Design rules: - “AI Integration” ERPNext user may create drafts only, never submit (enforced by role). - JSON-schema output; totals, taxes, GSTINs re-checked in code. - Source file attached; low-confidence results → “Needs Review”. - No HR/payroll data to AI. - Paid API only: Vertex AI asia-south1 for India residency (only some models, e.g. Gemini 3.5 Flash / 2.5 Flash, processed in India; check at build time). - Google Cloud budget alerts; every AI action logged.

| # | Flow | Build on | Starts | Risk |
| --- | --- | --- | --- | --- |
| A1 | Daily project & dispatch digest + COO/CFO summary: overdue tasks, drawings pending approval, POs over PCC, dispatches this week, BG expiries; from P4 major-value transactions, revenue/receipts vs purchases/expenses → Chat / WhatsApp / email (D7) | Apps Script time trigger → REST → Gemini → Chat webhook | P1 (Nov 2026) | Very low (read-only) |
| A2 | Enquiry → Lead: sales Gmail + IndiaMART/TradeIndia emails classified; company, country, machine type, billet size, capacity → Lead draft, duplicate check | Apps Script Gmail trigger or Workspace Studio → REST | P1 (Dec 2026) | Low |
| A3 | Supplier quotation PDF → Supplier Quotation draft + techno-commercial summary (rates, GST %, delivery, payment terms, validity, deviations) on the RFQ | n8n or Apps Script → Gemini (PDF) → match RFQ items → REST | P2 (Jan–Feb 2027) | Medium: item mapping; human check |
| A4 | Supplier bill → BRM + Purchase Invoice draft; GSTIN checksum, supplier match, CGST/SGST vs IGST by state code, totals (all in code) | n8n → Gemini → validation → REST (consider adapting erpocr_integration) | P4 (Apr–May 2027) | Medium: finance review mandatory |
| A5 | Meeting notes (Gemini in Meet/Doc) → Task drafts with owner, due date, project | Apps Script → Gemini → REST | P1+ | Low |
| A6 | Ask-ERP: natural-language, read-only, permission-aware questions | Frappe Assistant Core (MCP, AGPL) or frappe/mcp + Gemini CLI | P4 (mid 2027) | Medium: read-only role, logged |
| A7 | Drawing title block / BOM table → Item + BOM drafts (pilot) | Gemini on exported PDF/Excel BOMs; prefer CAD BOM exports | After P2, pilot | High for dense drawings; limit to title block + part list |

- Workspace extras (no build): Gemini in Gmail/Docs/Meet (level depends on Workspace Business edition; check MSCAST’s) for quotations, cover letters, summarising customer specs.

- Cost (estimate): ~US$0.02 per 5-page document on Gemini 3.5 Flash (Vertex regional); a few hundred documents a month = under ~US$10/month. Watch thinking-token usage; some Flash models reprice on 1 Jan 2027.

## 8. Indicative 3-year cost comparison (cash, excl. internal time)

| Item | ERPens proposal | Self-build | Basis |
| --- | --- | --- | --- |
| Implementation | ₹3.6 L + 18% GST ≈ ₹4.25 L | ₹0 cash (implementer’s time) + optional Pune freelancer for training/accounts cut-over ₹0.5–1.5 L (estimate) | Proposal; freelancer rate unverified |
| Hosting (36 months) | AWS ₹10k/month after month 1 ≈ ₹3.5 L (“may increase”) | Frappe Cloud Mumbai ≈ ₹4–5.5k/month ≈ ₹1.5–2.0 L (VPS similar) | Frappe Cloud price page; confirm bench + site at sign-up |
| Support | Optional ₹25k/month + GST (incl. cloud, 20 dev-hrs) ≈ ₹10 L over ~33 months, replacing AWS line | Own; Frappe community; paid help as needed | Proposal |
| India Compliance API credits | Not mentioned | Needed for e-way bill/e-invoice/GSTIN checks: get quote (500 free) | Price not published |
| Gemini / Google Cloud | n/a | ₹0.1–0.4 L over 3 years (estimate, with buffer) | Published per-token prices |
| Tally | Not addressed | TSS until FY26-27 audit closes (~₹5–15k) | Tally price page |
| 3-year total | ≈₹7.8 L (no support) · ≈₹12.5–14 L (with support; excl./incl. GST) | ≈₹2.5–4.5 L + credits |  |

Self-build effort: custom + configuration ≈28 person-weeks (doc 03 Summary sheet); with setup, migration, training, UAT ≈35–45 person-weeks over ~10 months; AI track +6–10 weeks. Key-person risk mitigated by Git repo, staging, runbook, documented fixtures, option to hire a Frappe partner for specific tasks.

## 9. Custom app backlog (mscast_erp, as planned)

Sizes: S ≤2 days · M 3–6 days · L 7–12 days. “No-code” = ERPNext settings screens (custom forms/fields, workflows, print formats, Server Scripts), exported into the app.

| # | Feature | Approach | Phase | Size |
| --- | --- | --- | --- | --- |
| 1 | Project template + kick-off workflow + milestones (GA approval, BOM release, dispatch lots, erection, commissioning). Kick-off checklist: mandatory PCC, signed technical specs, sales MOMs, contract/scope; PO checked against agreed terms; notifies Engineering, Projects, Procurement, Finance; project code naming series | Config | P1 | S |
| 2 | Quotation cost-estimate sheet per machine family | No-code form + child tables | P1 | M |
| 3 | Technical questionnaire on Opportunity | Custom fields/child table | P1 | S |
| 4 | Drawing Register: revision table, customer-approval status, transmittals, superseded control, Drive links | Custom form + workflow + Server Script | P1 | L |
| 5 | ECR/ECN approval with impact list (BOM/MR/PO) | Custom form + workflow; auto-replacement later (Python) | P1/P2 | M |
| 6 | Engineering doc forms (“MDF”) | Custom form + print format | P1 | S–M |
| 7 | Techno-commercial comparison: custom technical scoring + built-in price comparison; custom print | Custom fields on Supplier Quotation + script report + print | P2 | M |
| 8 | Inspection plan / calendar: stage, final, third-party, per project and vendor | Custom form linked to PO/project + report | P2 | M |
| 9 | Free-issue material balance by vendor (ITC-04 support) | Standard subcontracting + report | P2 | S |
| 10 | Dispatch schedule vs contract; MDM → DI (direct-to-site, transport arrangement) with Annexure-I; billing & despatch schedule (consignor, transporter, LR no./date, invoice no./date); packing list; Delivery Note per lot (ship-from-vendor) | Custom fields, form, print formats, report | P3 | M |
| 11 | Retention tracker (optional retention receivable postings) | Payment terms + custom fields + report; postings in Python | P3/P4 | M |
| 12 | BG/LC and PBG register with expiry alerts; LD exposure report | Standard Bank Guarantee + notifications + report | P3 | S–M |
| 13 | Completion certificate | Custom form + print | P3 | S |
| 14 | Project P&L (estimate vs budget vs actual), cash-flow forecast | Script/query reports, dashboard | P4 | M–L |
| 15 | Warranty / serial / service visit setup | Config | P5 | S |
| 16 | AI integration user; custom fields ai_generated/ai_confidence/ai_raw_json; webhooks | Config + small code | AI track | S |
| 17 | PCC sheet per Sales Order/Project (component-wise estimated cost, make, supplier category; revisions, approval; baseline for procurement control and project MIS) + PO-vs-PCC variance report, approval when a PO exceeds the PCC, PCC status updates | Custom form + script report + server script | P1/P2 | L + M |
| 18 | BRM: Procurement certifies supplier bill/proforma/internal memo against the PO. Register in P2–P3 (Tally books); gates Payment Entry from P4 | Custom form + workflow + server script | P2/P4 | M |
| 19 | Project MIS (MSCAST template), project closure report, SO↔PO↔invoice tracker | Script reports | P1/P4 | M + M |
| 20 | Additional client claims; Commissioning/PAC/FAC certificates; proforma print | Custom forms + print formats | P3 | S |
| 21 | Man-hours equipment-wise and project-wise; activity types (layout, detail design, hydraulics, P&ID, vendor visit, site) roll cost to the project | Custom field + report | P1 | S |
| 22 | MSME/Udyam supplier fields + 45-day dues report | Custom fields + script report | P2/P4 | M |
| 23 | Auditor role (read-only), MSCAST Director role (approving), Design User; incomplete-data alerts; archival SOP | Config | P0/P4 | S |
| 24 | Daily COO/CFO summary (email digest + WhatsApp/Chat or DLT SMS) | Config + small scheduled job | P4 | M |
| 25 | Project WIP valuation (per D6) | Config or small script | P3/P4 | M |
| 26 | Customer-owned (Tata Motors) asset register | Custom form | P4 | S |
| 27 | Biometric access-control attendance connector | Integration | P5 | M |

## 10. Decisions

| ID | Decision | Recommendation (16 Sep 2026) | Needed by | Status (21 Sep 2026) |
| --- | --- | --- | --- | --- |
| D1 | Hosting: Frappe Cloud Mumbai vs self-managed India VPS | Frappe Cloud (private bench) for P0–P5; revisit at 12 months | P0 (early Oct 2026) | Decided: self-managed India VPS (doc 08). Move parked by the owner |
| D2 | Accounts leave Tally on 1 Apr 2027 vs keep Tally permanently | Move on 1 Apr 2027, subject to CA dry-run sign-off (G3) | CA meeting in P0; final at G3 | Open |
| D3 | Payroll: india-payroll vs current provider (PF/ESI/PT/TDS required) | india-payroll after 2 parallel cycles (Jun–Jul 2027), subject to the PT bug check | P5 | Open |
| D4 | ERPens: decline, renegotiate, or retain for specific tasks | Decline the fixed-bid proposal; optionally a paid on-call Frappe expert (ERPens or a Pune partner) for the accounts cut-over | Now | MSCAST’s decision. The implementer is not competing with ERPens (unpaid demonstration for a family friend) |
| D5 | Google Cloud project for Vertex AI under MSCAST Workspace (billing owner, budget cap) | Create in P1 with a ₹1–2k/month budget alert | Before A1 | Answered by the build: not needed (local model router) |
| D6 | Project WIP valuation: Work Order + WIP warehouse vs Project WIP account + JV | Agree with CA; lighter JV method unless stage-wise WIP needed | Gate G2 (Jan 2027) | Open with the CA (doc 03, AC-17) |
| D7 | Daily COO/CFO summary channel: SMS (TRAI DLT, ≤40 chars per variable) vs WhatsApp utility template vs Google Chat/email | Email digest + WhatsApp or Google Chat; optional one-line DLT SMS | P3 | Open |
| – | Repository: transfer or mirror github.com/cb1-tech/mscast to MSCAST | – | – | Open |

## 11. Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| Key-person dependency (one builder, remote) | Git, staging, fixtures, runbook; named MSCAST key user per phase; optional partner retainer |
| Adoption at a ≤10-person firm used to WhatsApp and Excel | Operations-first phasing; mobile-friendly screens; daily digest (A1) makes the ERP the place to look; stop parallel Excel after each gate |
| Accounting/GST errors at cut-over | Financial-year boundary, CA dry-run, Tally read-only fallback |
| India Compliance credit costs | Disable unneeded GSTIN validations; watch the usage report |
| Young apps (india-payroll, AI community apps) | Parallel runs; pin versions; thin integrations |
| AI mistakes or prompt injection from external PDFs/emails | Draft-only role, code-side validation, no auto-submit, logging |
| Unclear requirements (“Finance Scaling Management”, “GST on closing inventory”, Tata Motors assets) | Resolve open questions at G0; defer, do not guess |
| Compliance expectations beyond ERP (Ind AS list, 8-year vendor undertaking) | CA confirms AS/SMC status; archival SOP + open-source licence in place of an undertaking |
| Biometric device incompatibility | Get device model in P0; budget a connector or device replacement |
| Scope creep (e.g. export docs, full PLM) | Backlog with phase gates; changes go to the next phase |

## 12. Next steps (as planned 16 Sep 2026)

- Sanjay reviews this plan and doc 03; decides D1, D4, D5; sends MSCAST the open questions (doc 03, Q1–Q21) and the format request (PCC, MIS, BRM, MDM, DI, Annexure-I). Current request: doc 10.

- Book the discovery workshop (2 × 2-hour video sessions) using the KB question list; collect samples (quotation, PO, BOM/drawing list, dispatch memo, invoice, retention letter, BG).

- Book the CA session (D2, e-invoice applicability, HSN/SAC, ITC-04).

- Provision hosting (staging first), domain, Google Sign-In; Git repo (done: github.com/cb1-tech/mscast).

- Prepare master-data Google Sheets templates for MSCAST to fill.

Sources: doc 02, section E.