## README
MSCAST ERP – Requirements Traceability Workbook
Version 2.0 · 21 September 2026 · matches doc 03 (Requirements Traceability) v3.0
What this workbook answers
1. Did the system cover everything MSCAST asked for? → sheet "From MSCAST requirements": the 97 requirements in MSCAST's document ERP_Requirement_Final.pdf, how each is met, and where to see it working.
2. What was added beyond the requirement document to make it a working, safe system for MSCAST? → sheet "Added to make it work": each addition, in plain words, with the requirement it protects.
3. What does MSCAST (or the CA) still have to answer? → sheet "Open Questions". Yellow cells are for the answer.
Totals for all three are on the "Summary" sheet and recalculate from the other sheets.
The two systems
Live POC: https://mscast.carobar.net – MSCAST staff are trying it with their own logins.
DEV: https://mscastdev.carobar.net – full demonstration data; the "Evidence" column refers to documents you can open there.
Column legend (From MSCAST requirements)
Type: Standard = ERPNext out of the box · Config = settings, roles, print formats, alerts · Custom = new forms, reports or rules built for MSCAST · Integration = connects an outside device · External = done outside the ERP (CA, policy).
Status: "Working" = live in the POC and shown on DEV · "Working – assumption to confirm" = built on an assumption MSCAST or the CA must confirm (see the Assumption column).
Phase and Size are from the original plan (P1–P5; S/M/L effort band) and are kept for reference.
"In ERPens proposal" is the implementer's reading of the ERPens scope document, not confirmed by ERPens.

## Summary
Summary
Where the system comes from
Basis | Items | Share
From MSCAST requirements | 97 | 80.83%
Added to make it work | 23 | 19.17%
Total | 120
MSCAST requirements by status
Status | Count
Working | 91
Working – assumption to confirm | 6
Not working | 0
Changed by MSCAST | 0
Total | 97
MSCAST requirements by type
Type | Count
Standard | 48
Config | 23
Custom | 22
Integration | 1
External | 1
Open question | 2
Total | 97
MSCAST requirements by area
Area | Count
Sales | 5
Projects | 9
Project coordination | 19
Engineering | 6
Procurement | 13
Erection & Commissioning | 1
Operations flow | 1
Accounts | 14
Management modules | 4
Accounts POV (compliance) | 2
Accounts POV (controls) | 3
Accounts POV (Companies Act s.128) | 1
Accounts POV (standards) | 1
Accounts POV (equity & liabilities) | 4
Accounts POV (assets) | 4
Accounts POV (inventory) | 3
Accounts POV (sales) | 1
Accounts POV (purchase) | 1
Accounts POV (expenses) | 4
Accounts POV (payroll) | 1
Total | 97
Additions by kind
Kind | Count
Safeguard | 6
Reliability | 7
Automation | 4
Presentation | 5
Documentation | 1
Open questions
Status | Count
Open | 21
Answered | 0
Not needed | 0

## From MSCAST requirements
ID | Area | Requirement (MSCAST document) | Source page | How the system meets it | Type (detail) | Type | Phase | Size | Status | Evidence on DEV (open these) | Assumption to confirm (who) | Open question | In ERPens proposal | Basis
S-01 | Sales | Prepare Sales Orders from customer orders | p2 | ERPNext Sales Order (customer PO no./date, payment terms template) | Standard | Standard | P1 | S | Working | 3 sales orders submitted with customer PO no., retention/LD/PBG fields |  |  | Yes | MSCAST requirement
S-02 | Sales | PCC sheet (Purchase Cost Calculation): cost price of each component of CCM/spares, prepared by Sales from the Sales Order | p2, p6 | Custom 'PCC' doctype linked to Sales Order/Project: component lines, revisions + approval; baseline for PO control and project MIS | Custom (no-code + script report) | Custom | P1 | L | Working | PCC-2026-00001 (R2, approved, 15 lines, Rs 1.82 Cr) and PCC-2026-00002 (approved). A director approves. A director may also prepare one (T6e, Q20) |  | Q2, Q20 | No | MSCAST requirement
S-03 | Sales | Order-status analysis; leads from customer enquiry or direct approach | p2 | CRM Lead → Opportunity → Quotation; Sales Pipeline Analytics | Standard | Standard | P1 | S | Working | Lead (Gulf Aluminium), 2 Opportunities, Quotation SAL-QTN-2026-00001; order-book chart. Plus 14 bid outcomes (6 won / 6 lost with reasons) |  |  | Yes | MSCAST requirement
S-04 | Sales | Scope of work/contract and PCC handed to Engineering and Projects | p2, p6 | Kick-off workflow on Project; mandatory attachments and notifications | Config | Config | P1 | S | Working | MSCAST Project Kickoff form with the 8-point customer-PO checklist, linked PCC / SO / project. Kick-off approval is a director's |  |  | Partly | MSCAST requirement
S-05 | Sales | List of potential/probable customers for forecasting | p2 | Leads/Opportunities with expected value and closing date | Standard | Standard | P1 | S | Working | Open lead + spares opportunity; 'Order Book by Customer' chart |  |  | Yes | MSCAST requirement
PR-01 | Projects | Internal kick-off meeting; Projects receives PCC, signed tech specs, sales MOMs | p2 | Project Template + kick-off checklist child table; Workflow 'Kick-off done' | Config | Config | P1 | S | Working | Project kick-off task completed on PROJ-0001, PCC + SO linked |  |  | Yes | MSCAST requirement
PR-02 | Projects | Project planning: targets for Engineering, Procurement, Despatch, Erection & Commissioning | p2 | Project tasks, milestones, dependencies, Gantt | Standard | Standard | P1 | S | Working | Tasks across 3 projects with dates, status and progress |  |  | Yes | MSCAST requirement
PR-03 | Projects | Prepare and submit Project Execution, Delivery and Billing schedules to client/consultant | p2, p6 | Delivery + billing schedule child tables on Project/SO; print formats | Config + light custom | Config | P1/P3 | M | Working | 'MSCAST Project Schedule (Client)' print - contractual milestones with live drawing, inspection, dispatch and commissioning status |  |  | Partly | MSCAST requirement
PR-04 | Projects | Periodic 'Overall Project Status/Schedule' submission to client | p2 | Project status print format/report | Custom (report + print) | Custom | P1 | M | Working | 'MSCAST Project Status Report' - progress bar, commercial and engineering position, open punch points |  |  | No | MSCAST requirement
PR-05 | Projects | Submit invoices and follow up receivables from client | p2 | Accounts Receivable, Payment Reminder/Dunning, Notification before due date | Standard | Standard | P4 | S | Working | Payment request + AR ageing + overdue notification |  |  | Yes | MSCAST requirement
PR-06 | Projects | Project completion: completeness of supplies | p3 | Sales Order Analysis (ordered vs delivered), SO–DN tracking | Standard | Standard | P3 | S | Working | MSCAST Dispatch Schedule shows ordered vs delivered vs pending |  |  | Partly | MSCAST requirement
PR-07 | Projects | Additional claims discussion and settlement with client | p3 | Custom 'Client Claim' doctype → amended SO / additional invoice | Custom (no-code) | Custom | P3 | S | Working | Client Claim register + print; CLM-2026-00001 (Rs 6.85 L scope variation, agreed Rs 6.40 L) and CLM-2026-00002 (idle time, settled by supplementary invoice) |  | Q14 | No | MSCAST requirement
PR-08 | Projects | Obtain Commissioning, Preliminary and Final certificates from client | p3, p6 | Custom 'Project Certificate' doctype; triggers milestone billing and retention clock | Custom (no-code) | Custom | P3 | S | Working | Certificates across projects with retention due date + print format |  |  | Yes (completion certificate) | MSCAST requirement
PR-09 | Projects | After final closure, hand over project info to Spares Dept for spares business | p3 | Project closure checklist; installed-machine record + customer spares price list | Config | Config | P5 | S | Working | MSCAST Spares Handover + print. Plus the MSCAST Installed Machine register: 14 machines, 2009–2024, the basis of the spares and retrofit business |  | Q15 | No | MSCAST requirement
PC-01 | Project coordination | Check customer PO against agreed terms; forward to Finance and Procurement | p3, p6 | SO approval workflow with PO-vs-quotation check; notifications | Config | Config | P1 | S | Working | 'MSCAST Project Kick-off' workflow: Draft → PO Verified (Accounts, only when price, scope, payment terms and GST are ticked) → Kick-off Approved (director); PROJ-0002 sits in 'PO Query Raised' because the customer's payment terms differ from the offer |  | Q20 | Partly | MSCAST requirement
PC-02 | Project coordination | Give billing and dispatch schedule to Procurement based on PCC | p3, p6 | Schedule child tables visible in Procurement workspace; report | Config | Config | P2 | S | Working | 'Billing / Dispatch Schedule' child table on the Project + report, carrying the action note per milestone |  |  | Partly | MSCAST requirement
PC-03 | Project coordination | Check supplier POs against PCC requirement and commercial terms | p3, p6 | Validation + 'PO vs PCC' variance report; approval required if over PCC | Custom (script report + server script) | Custom | P2 | M | Working | MSCAST PO vs PCC Variance report + PO PCC fields + 'PO over PCC' notification |  | Q2 | No | MSCAST requirement
PC-04 | Project coordination | Issue Delivery Instruction to supplier for dispatch to customer site | p3, p4, p6 | Custom 'Delivery Instruction' doctype from PO/MDM | Custom (no-code) | Custom | P3 | M | Working | DI-2026-00001 with consignee, transporter, LR, vehicle + print format |  | Q5 | Yes | MSCAST requirement
PC-05 | Project coordination | Free-issue list dispatched with Delivery Instruction to sub-contractor | p3 | Subcontracting supplied items / Stock Entry; Annexure-I print | Standard + print format | Standard | P2/P3 | S | Working | Free-issue stock transfer to 'Free Issue at Vendor' + Annexure-I on the DI print |  |  | Yes | MSCAST requirement
PC-06 | Project coordination | Receive purchase bills, check against PO and Delivery Instruction; original to Accounts, duplicate to Purchase for BRM | p3 | BRM register records supplier bill against PO; Purchase Invoice with certification workflow | Custom → Standard + workflow | Custom | P2/P4 | M | Working | 3 BRMs against POs. Workflow: Purchase prepares → a director certifies → Accounts marks paid. A director can also do all three steps alone (T6g, Q21) |  | Q21 | No | MSCAST requirement
PC-07 | Project coordination | Prepare Sales Invoice, Delivery Challan and Packing List | p3, p7 | Delivery Note, Packing Slip, Sales Invoice; e-way bill | Standard | Standard | P3/P4 | S | Working | 6 sales invoices, 3 delivery notes; packing slip not demoed |  |  | Yes | MSCAST requirement
PC-08 | Project coordination | Update stock items and free-issue statement | p3 | Stock Ledger; vendor-wise free-issue balance report | Standard + report | Standard | P2 | S | Working | MSCAST Free Issue at Vendor report (plate + sections at vendor) |  |  | Yes | MSCAST requirement
PC-09 | Project coordination | Update billing & despatch schedule with consignor, transporter, LR no./date, invoice no./date | p3 | Delivery Note transporter/LR/vehicle fields + schedule-vs-actual report | Standard + report | Standard | P3 | S | Working | DN carries transporter, LR no./date, vehicle; dispatch schedule report |  |  | Partly | MSCAST requirement
PC-10 | Project coordination | Project code allocation | p3 | Project naming series | Config | Config | P0 | S | Working | PROJ-0001 / 0002 / 0003 |  |  | Yes | MSCAST requirement
PC-11 | Project coordination | Update ongoing/new and executed/closed project and Sales Order lists | p3 | Project and Sales Order list views/reports with status filters | Standard | Standard | P1 | S | Working | List views with status filters |  |  | Yes | MSCAST requirement
PC-12 | Project coordination | Maintain supplier and customer information | p3 | Customer/Supplier masters (GSTIN, PAN, MSME/Udyam, contacts, addresses) | Standard + custom fields | Standard | P0/P1 | S | Working | 13 customers, 15 suppliers with GSTIN, state, MSME type and addresses. GSTIN check digits and pincode-to-state validated on entry |  |  | Yes | MSCAST requirement
PC-13 | Project coordination | New Project MIS as per given template | p3 | Custom project MIS report per MSCAST template | Custom (script report) | Custom | P1/P4 | M | Working | MSCAST Project MIS report (contract vs PCC vs PO vs billed vs hours) |  | Q3 | No | MSCAST requirement
PC-14 | Project coordination | Project completion accounting closure reports | p3 | Project Profitability + custom closure report | Custom (script report) | Custom | P4 | M | Working | 'MSCAST Project Closure Report' with a closure verdict per project |  |  | No | MSCAST requirement
PC-15 | Project coordination | Pending Sales Order review | p3 | Sales Order Analysis / pending items to deliver and bill | Standard | Standard | P1 | S | Working | Pending quantities in the dispatch schedule report |  |  | Yes | MSCAST requirement
PC-16 | Project coordination | Material movement tracking | p3 | Stock Ledger, Project-wise Stock Tracking, DI/Delivery Note status | Standard + report | Standard | P2/P3 | S | Working | Stock ledger, project-wise stock, stock entries, DI/DN status |  |  | Partly | MSCAST requirement
PC-17 | Project coordination | Proforma Invoice for advance/scheduled supply per SO payment terms | p3 | 'Proforma Invoice' print format on Sales Order + Payment Request | Config (print format) | Config | P3 | S | Working | 'MSCAST Proforma Invoice' + advance payment request |  |  | No | MSCAST requirement
PC-18 | Project coordination | Supplementary Invoice for retention amount | p3 | Payment Terms Template + retention tracker; Retention Receivable account | Custom | Custom | P3/P4 | M | Working | Retention reclassified to Retention Receivable on two projects; supplementary invoice against the agreed claim |  |  | Yes (retention tracking) | MSCAST requirement
PC-19 | Project coordination | Track Sales Order vs Purchase Order vs Supply Invoice | p3 | Custom tracker report SO ↔ PCC ↔ PO ↔ PI ↔ SI | Custom (script report) | Custom | P3/P4 | M | Working | 'MSCAST SO - PO - Invoice Tracker' per order |  |  | No | MSCAST requirement
E-01 | Engineering | Receive PCC / division scope list | p4 | Link on Project; notification | Config | Config | P1 | S | Working | PCC linked from the project; engineering tasks assigned |  |  | Partly | MSCAST requirement
E-02 | Engineering | Prepare engineering programme and design/drawings | p4, p6 | Engineering tasks + Drawing Register (revisions, approvals, transmittals, Drive links) | Custom (no-code + workflow) | Custom | P1 | L | Working | 9 drawings with revision tables and Drive links; MSCAST Drawing Register report. 'MSCAST Drawing Release' workflow: Draft → For Customer Approval → Approved by Customer → Released for Manufacture → Superseded. Only a Projects Manager releases, and only from *Approved by Customer* |  |  | Yes | MSCAST requirement
E-03 | Engineering | Prepare MDF once drawings are final | p4, p6 | Engineering BOM or custom 'MDF' doctype with print; generates Material Requests | Config + custom print | Config | P1 | M | Working | 3 MDFs (WSU, Mould, Hydraulics) + MDF print format |  |  | Yes | MSCAST requirement
E-04 | Engineering | Finalise extra bought-out item list | p4, p6 | Bought-out item groups; Material Request from BOM/MDF | Standard | Standard | P1/P2 | S | Working | Bought-out item groups; Material Request raised from the MDF lists |  | Q18 | Yes | MSCAST requirement
E-05 | Engineering | Send MDF and bought-out list to Procurement; follow up | p4 | MDF submit → Material Request + notification; Procurement Tracker report | Config | Config | P2 | S | Working | MSCAST Transmittal register + note print; drawing set issued to the customer (acknowledged) and to the fabricator |  |  | Yes | MSCAST requirement
E-06 | Engineering | Capture engineering man-hours equipment-wise and project-wise | p8 | Timesheet with custom 'Equipment' field + man-hour report | Config + custom field/report | Config | P1 | S | Working | Timesheets with Equipment field; 'Engineering Hours by Activity' chart. The overnight sweep flags any open project with no time ever booked |  | Q17 | Yes (manhours) | MSCAST requirement
P-01 | Procurement | Receive PCC, drawings, MDF and bought-out list | p4 | Links from Material Request to PCC/Drawing/MDF | Config | Config | P2 | S | Working | PCC, drawings and MDF linked into the procurement flow |  |  | Partly | MSCAST requirement
P-02 | Procurement | Send enquiries to vendors | p4, p6 | Request for Quotation | Standard | Standard | P2 | S | Working | PUR-RFQ-2026-00001 to 3 suppliers for 3 items |  |  | Yes | MSCAST requirement
P-03 | Procurement | Techno-commercial comparison of offers and supplier selection | p4, p6 | Supplier Quotation Comparison + custom technical scoring fields | Custom (light) | Custom | P2 | M | Working | 2 supplier quotations with technical score, compliance, deviations, recommended flag |  |  | Yes | MSCAST requirement
P-04 | Procurement | Release PO with technical specifications, price, terms and conditions | p4, p6 | Purchase Order + T&C templates + spec attachments | Standard + print format | Standard | P2 | S | Working | Purchase orders with terms, PCC reference and budget. A Purchase User sends for approval; a director approves. Nobody holds both roles, so every PO passes through two people |  | Q18 | Yes | MSCAST requirement
P-05 | Procurement | Release drawings and MDF to equipment manufacturers | p4, p6 | Drawing transmittal from Drawing Register | Custom (part of E-02) | Custom | P2 | S | Working | TRN-2026-00002 to Pushkar Fabricators with revision and sheet counts |  |  | Partly | MSCAST requirement
P-06 | Procurement | Arrange bought-outs and supply them to the manufacturer | p4, p6 | Subcontracting supplied items / Stock Entry to vendor | Standard | Standard | P2 | S | Working | Free issue of plate and sections to the fabricator |  |  | Yes | MSCAST requirement
P-07 | Procurement | Supplier follow-up; coordinate inspection of equipment and bought-outs | p4, p6 | Quality Inspection Templates + custom Inspection Plan per PO/project | Standard + custom | Standard | P2 | M | Working | 4 inspection plans + templates on 4 items + 2 incoming inspections |  |  | Yes | MSCAST requirement
P-08 | Procurement | Release supplier payments against invoice/proforma/internal memo invoice with certification via Billing Routing Memo (BRM) to Accounts | p4, p5, p6 | Custom 'BRM' doctype + workflow; Payment Entry and Journal Entry allowed only against a certified BRM | Custom (no-code + application code) | Custom | P2/P4 | M | Working | 3 BRMs + print format + BRM Register report. Purchase prepares and may reject; a director certifies (certifying releases the money); Accounts marks paid. A BRM cannot be certified unless its four checks (qty, rate, inspection, delivery) are ticked (T6n). Limitation (T6g, Q21): a director also holds the roles that create a BRM and mark it paid, so a certificate does not prove three people were involved. The payment block holds for everyone |  | Q4, Q21 | No | MSCAST requirement
P-09 | Procurement | Track POs against PCC and update status (PCC updation) | p4, p6 | PO vs PCC report + PCC status column | Custom (report) | Custom | P2 | S | Working | MSCAST PO vs PCC Variance report with committed % and variance |  | Q2 | No | MSCAST requirement
P-10 | Procurement | Collect vendor stock declaration of free-issue items project-wise | p4, p6 | Vendor-wise, project-wise supplied-item balance report | Standard + custom | Standard | P2 | S | Working | Free Issue at Vendor report by item and value |  |  | Yes | MSCAST requirement
P-11 | Procurement | Prepare Material Dispatch Memo (MDM) → Delivery Instruction to supplier | p4, p6 | Custom 'MDM' doctype → creates Delivery Instruction | Custom (no-code) | Custom | P3 | M | Working | MDM-2026-00001 with free-issue flag + print format |  | Q5 | Yes | MSCAST requirement
P-12 | Procurement | Free-issue items list as Annexure-I with MDM | p4, p6 | Annexure-I print format from MDM/Subcontracting data | Config (print format) | Config | P3 | S | Working | Annexure-I printed with the Delivery Instruction |  | Q5 | Partly | MSCAST requirement
P-13 | Procurement | Performance Bank Guarantee (PBG) certification | p6 | Bank Guarantee doctype + expiry notifications + BG register | Standard + config | Standard | P3 | S | Working | 2 bank guarantees (ABG + PBG) with validity + 30-day expiry notification. The overnight sweep also raises an exception as expiry approaches |  |  | No | MSCAST requirement
EC-01 | Erection & Commissioning | Erection and commissioning of CCM at site | p6, p7 | Site tasks, site timesheets, Expense Claims, commissioning report | Standard + config | Standard | P3 | S | Working | MSCAST Commissioning Report: 5 performance parameters, 6 trial heats, punch list, provisional acceptance + signature print |  |  | Partly | MSCAST requirement
EC-02 | Operations flow | Inspection → Packing → Loading → Transport → Commissioning | p7 | Quality Inspection gate before Delivery Note; Packing Slip; e-way bill | Standard + config | Standard | P2/P3 | S | Working | Quality inspection → delivery note with transport details; packing slip not demoed |  |  | Partly | MSCAST requirement
A-01 | Accounts | Check PO and contract before giving credit to vendor | p5 | Supplier payment terms; Purchase Invoice linked to PO; hold/approval | Standard | Standard | P4 | S | Working | Supplier credit limit set + PO/contract check |  |  | Yes | MSCAST requirement
A-02 | Accounts | Purchase voucher entries for bought-outs and equipment with taxes, duties, freight | p5, p6 | Purchase Invoice with tax templates; Landed Cost Voucher | Standard | Standard | P4 | S | Working | Landed cost voucher MAT-LCV-2026-00001 (Rs 45,000 freight) apportioned onto the mould-tube receipt |  |  | Yes | MSCAST requirement
A-03 | Accounts | Check purchase invoices against PO qty, rates, terms | p5 | PO–PR–PI matching; over-billing allowance = 0 | Standard | Standard | P4 | S | Working | Purchase invoice matched to the purchase receipt and PO |  |  | Yes | MSCAST requirement
A-04 | Accounts | Sales entry from sales invoice raised by project coordinator | p5 | Sales Invoice (e-invoice if applicable) | Standard | Standard | P4 | S | Working | Intra-state CGST+SGST, inter-state IGST and services invoices |  |  | Yes | MSCAST requirement
A-05 | Accounts | Project payments only after BRM from Procurement | p5, p6 | Payment Entry and Journal Entry validation against a certified BRM | Custom (application code, mscast_erp.controls.brm_payment) | Custom | P4 | S | Working | Tested on six routes on every build (T6a): a bill with no certified BRM cannot be paid by Payment Entry, by Journal Entry, or as an advance with no reference; a payment above the certified amount is refused; an already-paid BRM cannot fund a second payment. Holds for every user, including a director. Utilities, rent and statutory bills are released by ticking *Exempt from BRM certification* on the supplier (0 of 15 suppliers ticked; MSCAST to list them). App code, so it is version-controlled and shipped in the image |  | Q4, Q21 | No | MSCAST requirement
A-06 | Accounts | Non-project payments: admin, utilities, credit cards, government, salary | p5 | Payment Entry / Journal Entry | Standard | Standard | P4 | S | Working | 6 journal vouchers: electricity, petty cash imprest and spend, foreign travel, insurance, cargo agency |  |  | Yes | MSCAST requirement
A-07 | Accounts | Petty cash payments | p5 | Petty cash account + Mode of Payment; Employee Advance for imprest | Config | Config | P4 | S | Working | Petty Cash account + 'Cash' mode of payment |  |  | Yes | MSCAST requirement
A-08 | Accounts | Customer receipts and receipt to customer | p5 | Payment Entry (Receive) + receipt print format | Standard | Standard | P4 | S | Working | Advance receipts against ABG across projects |  |  | Yes | MSCAST requirement
A-09 | Accounts | Cheque printing | p5 | Cheque Print Template (bank-wise) | Standard | Standard | P4 | S | Working | 'MSCAST Payment Receipt' print format with amount in words and allocation table; HDFC cheque template configured |  |  | No | MSCAST requirement
A-10 | Accounts | Cash receipts against travel advances and sale of old items | p5 | Employee Advance return; asset/scrap sale invoice | Standard | Standard | P4/P5 | S | Working | Configured |  |  | Yes | MSCAST requirement
A-11 | Accounts | Debit/credit notes per PO terms | p5, p6 | Debit Note / Credit Note | Standard | Standard | P4 | S | Working | Credit note (sales rejection) and debit note (rate difference) |  |  | Yes | MSCAST requirement
A-12 | Accounts | Journal vouchers: travel, asset purchase, insurance, year-end, cargo agencies | p5, p6 | Journal Entry; multi-currency Expense Claim; Landed Cost Voucher | Standard | Standard | P4 | S | Working | Foreign travel, marine + erection insurance, cargo agency vouchers |  | Q16 | Yes | MSCAST requirement
A-13 | Accounts | Monthly MIS reflecting monthly project costs | p5 | Cost Centre/Project dimension P&L + PCC vs actual MIS | Custom (report) | Custom | P4 | M | Working | MSCAST Project MIS + PO vs PCC variance. Every ledger entry is checked to carry a cost centre |  | Q3 | Partly | MSCAST requirement
A-14 | Accounts | Monthly Balance Sheet, P&L, Funds Flow / Cash Flow | p5 | Balance Sheet, P&L, Cash Flow; Schedule III templates | Standard | Standard | P4 | S | Working – assumption to confirm | Schedule III balance sheet and P&L in the statutory vertical format - verified to balance to the rupee and the profit ties to the ledger surplus. Plus the 2021-amendment disclosures and the eleven prescribed ratios (guarded so immaterial denominators show n/a). ASSUMPTION: format still to be signed off by the CA | CA | Q10 | Yes | MSCAST requirement
M-01 | Management modules | Employee management: leave, attendance, hours, salary slips | p8 | Frappe HR + india-payroll salary slips | Standard | Standard | P5 | M | Working | 6 employees, 150 attendance records, leave, 6 salary slips, expense claim |  | Q12 | Yes | MSCAST requirement
M-02 | Management modules | Finance Scaling Management | p8 | Unclear requirement | Open question | Open question | P0 | – | Working – assumption to confirm | 'MSCAST Finance Scaling - Funding and Capacity': order book and pipeline against scheduled collections, committed outflows, cash, the Rs 2.5 Cr sanctioned HDFC limit and the projected 90-day headroom. ASSUMPTION: read as "can the business fund the order book it is chasing" (Q1) | MSCAST (Q1) | Q1 | No | MSCAST requirement
M-03 | Management modules | Biometric door lock/unlock integration for attendance | p8 | Employee Checkin API + Shift Type auto-attendance; device sync agent | Integration | Integration | P5 | M | Working – assumption to confirm | Shift type with auto attendance; 72 punches from device MSCAST-DOOR-01 converted into Attendance, plus the audit report (on DEV; on the Live POC MSCAST's trial admin deleted the punches, so T10c fails there). The scheduled pull job is off; enable it and prove it against manually checked attendance before payroll relies on it. ASSUMPTION: no device model given, so the standard push pattern is modelled (Q6) | MSCAST (Q6) | Q6 | No | MSCAST requirement
M-04 | Management modules | Customer & supplier management | p8 | Customer/Supplier masters, portal, scorecard | Standard | Standard | P1 | S | Working | Masters with GST, MSME, capability and scorecard |  |  | Yes | MSCAST requirement
AC-01 | Accounts POV (compliance) | Audit trail facility (MCA rule from 1 Apr 2023) with auditor login | p10 | India Compliance audit trail (cannot be disabled once on) + a read-only auditor role + Accounting Period freeze | Config | Config | P0/P4 | S | Working | Audit trail enabled before first entry. Auditor role: read / report / print / export only, including Version history and GL Entry; no write anywhere. Held on DEV by the CA login (S. Joshi); that login was deleted on the Live POC. MSCAST Director is the approving role, not a read-only one |  |  | No | MSCAST requirement
AC-02 | Accounts POV (compliance) | Edit log of each transaction in ERP | p10 | Version log on all ledger doctypes; 'Audit Trail' report | Standard | Standard | P0 | S | Working | Version log + India Compliance Audit Trail report |  |  | Partly (audit trail) | MSCAST requirement
AC-03 | Accounts POV (controls) | Alerts for incomplete data, masters and transactions | p10 | Notifications + Auto Email Reports on saved 'missing data' reports | Config | Config | P1→P4 | S | Working | 9 enabled notifications (BG expiry, PO over PCC, drawing approval) + scheduled reports, all resolving to a live mailbox (checked on every build-check run). Plus the 16-rule overnight sweep at 06:00 IST |  |  | No | MSCAST requirement
AC-04 | Accounts POV (controls) | Emailing of all possible outputs | p10 | Email button with PDF print format; Notification attach print; Auto Email Report | Standard | Standard | All | S | Working | Outgoing mail live through Purelymail; SPF, DKIM and DMARC all pass at Gmail; site host_name set so document links resolve publicly |  |  | Yes | MSCAST requirement
AC-05 | Accounts POV (controls) | Daily SMS to COO/CFO: major-value transactions; revenue & receipts vs purchases & expenses; MIS | p10 | SMS needs TRAI DLT registration and fixed templates - poor fit for a multi-figure summary. Email / WhatsApp / Google Chat recommended | Config + custom (small) | Config | P2 / P4 | M | Working | Daily management summary (20 indicators with an Attention column) at 08:30 IST to autoelectron.jp@gmail.com; AI morning briefing at 08:35 IST, ranking the day's exceptions with every item linked, to waseemraj@mcast.co.in on the Live POC (owner's decision). Google Chat webhooks for transactions above Rs 5 L are configured and disabled until MSCAST gives the space URL |  | Q7 | No | MSCAST requirement
AC-06 | Accounts POV (Companies Act s.128) | Books in electronic mode; director inspection; 8-year retention; ERP provider undertaking | p11 | India VPS with daily India backups (Rule 3(5)); GPL software cannot be withdrawn; yearly archive dumps; IT policy | Config + policy | Config | P0/P4 | S | Working | MSCAST Archival Log + monthly scheduled script + 8-year retention note + rolling backups; nightly backup at 02:30 JST with all build checks. Off-site India copy is a production step |  | Q13 | No | MSCAST requirement
AC-07 | Accounts POV (standards) | Indian Accounting Standards list | p12 | MSCAST likely follows Companies (AS) Rules 2021 as an SMC; Ind AS applies only at net worth ≥ ₹250 Cr | External (CA) | External | P0 | – | Working – assumption to confirm | 'MSCAST Notes to Accounts' - 25 notes including MSMED s.22, related party (AS 18), contingent liabilities from live bank guarantees, CWIP ageing, EPS basis, audit-trail note and the Schedule III negative disclosures. ASSUMPTION: SMC reporting under AS, stated on the face of the note | CA | Q10 | No | MSCAST requirement
AC-08 | Accounts POV (equity & liabilities) | Share capital: authorised, issued; reconciliation of shares; >5% shareholders; rights | p13 | Share capital accounts; Shareholder/Share Transfer records | Config / External | Config | P4 | S | Working | 3 shareholders, Share Type Equity, 10,000 equity shares of Rs 10 (paid-up Rs 1,00,000). Held as Promoter A / B / C, so invented percentages are not attributed to MSCAST's real directors |  | Q19 | No | MSCAST requirement
AC-09 | Accounts POV (equity & liabilities) | Reserves & surplus; borrowings; lease liabilities | p13 | Chart of accounts (Schedule III grouping); lease entries by JV | Config | Config | P4 | S | Working | Reserves and Surplus, Borrowings - HDFC Term Loan, Lease Liabilities, Prior Period Expenses, Fines and Penalties, Retention Receivable, Petty Cash |  |  | Partly | MSCAST requirement
AC-10 | Accounts POV (equity & liabilities) | Trade payables split: micro & small enterprises vs others | p13 | Custom Supplier fields (Udyam no., class) + 45-day dues report | Custom (fields + script report) | Custom | P2 / P4 | M | Working | Suppliers tagged Micro/Small with Udyam numbers; 'MSCAST MSME 45-Day Dues' report with days-beyond-45 and disallowance flag. The overnight sweep raises an exception as a bill approaches day 45 |  |  | No | MSCAST requirement
AC-11 | Accounts POV (equity & liabilities) | Provisions: gratuity, actuarial valuation & entries; income tax; deferred tax | p13 | Frappe HR Gratuity; liability valuation external → JV; tax & deferred tax by JV | Standard + External | Standard | P5 / P4 | S | Working – assumption to confirm | Gratuity Rule + provision Rs 9.91 L; current tax Rs 15.33 L at 25.168% (s.115BAA) on PBT Rs 60.90 L; deferred tax with DTA on gratuity and DTL on depreciation timing. ASSUMPTIONS stated in each voucher narration | CA | Q12 | No | MSCAST requirement
AC-12 | Accounts POV (assets) | Fixed asset register: additions, asset ID, disposals, depreciation | p14 | Asset with depreciation schedules, two Finance Books, disposal/scrap | Standard + config | Standard | P4 | S | Working | 4 assets submitted with depreciation schedules |  |  | Yes | MSCAST requirement
AC-13 | Accounts POV (assets) | Identification of own assets vs customer-owned assets | p14 | Separate register (custom doctype) | Custom (small) | Custom | P4 | S | Working | MSCAST Customer Asset register - customer-supplied mould tube set and gauges held at the sub-contractor, explicitly not capitalised |  | Q8 | No | MSCAST requirement
AC-14 | Accounts POV (assets) | Intangible assets: software, life, amortisation, under development | p14 | Intangible Asset Category with SLM amortisation; CWIP | Config | Config | P4 | S | Working | 'Software (Intangible)' category + ERP licence Rs 2.40 L amortised over 36 months |  |  | Partly | MSCAST requirement
AC-15 | Accounts POV (assets) | Capital work-in-progress list with completion status | p14 | CWIP accounting on Asset Category + Asset Capitalization | Standard + config | Standard | P4 | S | Working | 'Plant under construction (CWIP)' category; Rs 7.80 L in CWIP; available for use in 3 months |  |  | No | MSCAST requirement
AC-16 | Accounts POV (inventory) | Closing stock register category-wise and item-wise | p14 | Stock Balance by item group/warehouse | Standard | Standard | P2/P4 | S | Working | Stock Balance by item group and warehouse |  |  | Yes | MSCAST requirement
AC-17 | Accounts POV (inventory) | Working of valuation of semi-finished inventory (WIP) | p14 | Project WIP account + JV on sale | Custom / design decision | Custom | P3 / P4 | M | Working – assumption to confirm | 'MSCAST Project WIP Valuation' report carrying Rs 26.71 L. Method: bought-out billed + material issued + engineering hours at Rs 450/hr + 12% works overhead, less the cost of the billed portion. ASSUMPTION: method needs the auditor's blessing (D6) | CA (decision D6) | Q11 | No | MSCAST requirement
AC-18 | Accounts POV (inventory) | GST on closing inventory | p14 | Not a regular GST concept (ITC reversal only on cancellation) | Open question | Open question | P0 | – | Working | 'MSCAST GST on Closing Inventory (ITC and ITC-04)' - stock by warehouse with HSN, value, embedded ITC and the treatment note, separating stock at the job worker (ITC-04, one-year rule) from stock on own premises |  | Q9 | No | MSCAST requirement
AC-19 | Accounts POV (sales) | Sales reconciliation incl. with GSTR-1; rate difference; rejections | p15 | GSTR-1 (Books vs Filed); credit/debit notes; sales returns | Standard | Standard | P4 | S | Working | GST sales invoices with correct CGST/SGST vs IGST, checked against the place of supply on every invoice on every build-check run; GSTR-1 and GST Sales Register available |  |  | Yes (GST) | MSCAST requirement
AC-20 | Accounts POV (purchase) | Purchase reconciliation with GSTR; rejections | p15 | Purchase Reconciliation Tool (GSTR-2A/2B); purchase returns | Standard | Standard | P4 | S | Working | PINV with input IGST; Purchase Reconciliation Tool available |  |  | Yes (GST) | MSCAST requirement
AC-21 | Accounts POV (expenses) | Expenses: monthly volume, last-year comparison, ratio to sales | p15 | P&L Growth View and Margin View | Standard | Standard | P4 | S | Working | 'MSCAST Expense Analysis (vs last year, share of sales)' report |  |  | Partly | MSCAST requirement
AC-22 | Accounts POV (expenses) | TDS deduction on expenses | p15 | Tax Withholding Categories (194C/194J etc.) | Standard | Standard | P4 | S | Working | TDS 194C category (2%) on the fabricator, with TDS deducted on the invoice |  |  | Yes | MSCAST requirement
AC-23 | Accounts POV (payroll) | Monthly payroll matching all deductions: PF, ESI, PT, TDS | p15 | Salary Register + PF/ESI/PT/TDS registers | Standard (+ bug check) | Standard | P5 | M | Working | 6 salary slips with PF 12%, ESIC, Professional Tax MH and TDS; india_payroll registers need statutory config. v16 Maharashtra PT women-exemption bug to be checked before go-live |  | Q12 | Yes | MSCAST requirement
AC-24 | Accounts POV (expenses) | Prior period expenses; fines & penalties under any law | p15 | Separate GL accounts + JV tagging | Config | Config | P4 | S | Working | Both accounts created |  |  | No | MSCAST requirement
AC-25 | Accounts POV (expenses) | Warranty claims | p15 | Warranty Claim + Maintenance Visit; warranty provision account | Standard | Standard | P5 | S | Working | 1 open warranty claim against a spare roll |  |  | No | MSCAST requirement

## Added to make it work
ID | Kind | What was added | Why MSCAST needs it (plain words) | Protects requirement(s) | Where to see it | Automatic check (technical) | Basis
X-01 | Reliability | Installable application package (mscast_erp) | The same system can be installed on MSCAST's own server and upgraded safely. Nothing lives only on the builder's laptop. | All; AC-06 | Repository github.com/cb1-tech/mscast | T6m | Added by the implementer
X-02 | Reliability | One-step fresh install that tests itself | A clean production system can be built in one step, and it refuses to report success unless 19 system checks pass. | AC-06 | Script new-mscast-site.sh; doc 08 | T1–T7b (system set) | Added by the implementer
X-03 | Reliability | Nightly backup, with restore tested | Data can be recovered after a failure. The books must stay recoverable (Companies (Accounts) Rules r.3(5)). The backup carries the encryption key so saved passwords still work after a restore. | AC-06 | Windows task "MSCAST nightly backup" 02:30 JST; restore-test.sh | T9g, T9h | Added by the implementer
X-04 | Reliability | Backup watchdog and failure alerts | Someone is emailed if the nightly backup or the checks fail, or if the nightly job stops running. | AC-06 | Email to the implementer; 09:00 IST watchdog | T9h | Added by the implementer
X-05 | Reliability | 42 automatic checks, run every night | The system tests itself: reports run, prints render, the books balance, controls hold, permissions are right. Problems are caught before staff meet them. | AC-01, AC-03 | POC README, section "Build checks" | all | Added by the implementer
X-06 | Safeguard | Payment block on every way of paying a supplier | Money cannot go out on a supplier bill without a certified BRM – whether paid by Payment Entry, Journal Entry or as an advance, and not above the certified amount. Utilities, rent and statutory payees are marked exempt so they can still be paid. | P-08, A-05, A-06, PC-06 | Stop 6 of the demo run-sheet (doc 12) | T6a, T6c | Added by the implementer
X-07 | Safeguard | A BRM cannot be certified unless its four checks are ticked | Certification means quantity, rate, inspection and delivery were actually checked against the PO. | P-08, PC-06, A-03 | Any certified BRM on DEV, e.g. BRM-2026-00003 | T6n | Added by the implementer
X-08 | Safeguard | Kick-off held until the customer PO matches the offer | A project cannot start while the customer PO checklist is incomplete – differences in payment terms, LD, PBG are caught first. | PC-01, S-04, PR-01 | KICK-2026-00002 on DEV (held) | T6j | Added by the implementer
X-09 | Safeguard | Two people on every purchase order | Purchase sends the PO; a director approves it. One person cannot do both. | P-04, PC-03 | PUR-ORD-2026-00002 on DEV | T6d | Added by the implementer
X-10 | Safeguard | Drawings released for manufacture only after customer approval | Nothing is manufactured from a drawing the customer has not approved; only a Projects Manager releases. | E-02, P-05 | MSCAST Drawing Register on DEV | T6d | Added by the implementer
X-11 | Safeguard | Permissions per role, and a read-only login for the CA | Each person can open and do exactly what their role card says; the CA can read everything and change nothing. | AC-01, AC-02 | Role Cards (doc 09) | T6h, T6i, T6k, T6l | Added by the implementer
X-12 | Automation | Overnight exception check (16 rules, 06:00 IST) | Every morning a list of problems: uncertified bills, MSME payment deadlines, expiring bank guarantees, projects with no time booked, dispatch without paperwork. | AC-03, AC-10, P-13 | MSCAST Exception list | T9f | Added by the implementer
X-13 | Automation | Morning emails at 08:30 IST | Management summary, dispatch schedule and project MIS arrive by email – no login needed. | AC-04, AC-05, PC-13 | Email to the configured recipients | T9c | Added by the implementer
X-14 | Automation | AI morning briefing at 08:35 IST | A few plain sentences on what matters most today, each item linked. Falls back to a plain list if the AI service is unreachable. | AC-05 | Email (on the Live POC: waseemraj@mcast.co.in) | T9f | Added by the implementer
X-15 | Presentation | Director home page and dashboard | One page: cash, receivables, payables, order book, each project's margin and billing, and what needs attention today. | A-13, PC-13 | Home page as a director | T1b | Added by the implementer
X-16 | Presentation | Statutory pack for the CA | Schedule III balance sheet and P&L that balance to the rupee, ageing, the eleven prescribed ratios, 25 notes. | A-14, AC-07 to AC-16 | MSCAST Balance Sheet (Schedule III) | T5a–T5d | Added by the implementer
X-17 | Presentation | GST masters loaded | 18,687 HSN codes, GST accounts and tax templates, so invoices carry the right GST from day one. | AC-19, AC-20, PC-07 | Any sales invoice on DEV | T7c, T8 | Added by the implementer
X-18 | Presentation | MSCAST branding, letterhead and 15 print formats | Documents look like MSCAST's own. On the demo systems every print carries a DEMONSTRATION mark so it cannot be mistaken for a real invoice. | AC-04 | Print any PCC or proforma on DEV | T4, T4b | Added by the implementer
X-19 | Automation | Monthly archival job | Keeps records retrievable for the 8-year retention period. | AC-06 | MSCAST Archival Log | T9f | Added by the implementer
X-20 | Reliability | DEV copy of the system | Try changes, train staff and give demos without touching the Live POC. | — | https://mscastdev.carobar.net | — | Added by the implementer
X-21 | Reliability | Public web address with a valid certificate | Open the system from anywhere in a browser; no VPN or software to install. | — | https://mscast.carobar.net | — | Added by the implementer
X-22 | Presentation | Realistic demonstration data | 3 projects at different stages, 63 items, 28 parties, 14 installed machines, 6 employees with payroll – every screen shows real-looking numbers. | — | DEV | T7a | Added by the implementer
X-23 | Documentation | 13 documents | Setup guide, SOPs, role cards, operating rules, cutover runbook, demo run-sheet and others, so MSCAST is not dependent on one person's memory. | — | ERP Plan folder; the project | — | Added by the implementer

## Open Questions
# | Topic | Question | Related requirement IDs | Who answers | Needed by | Answer (fill in) | Status
Q1 | Finance Scaling Management | What exactly is meant (budgets, cash-flow forecasting, multi-entity growth, credit limits)? | M-02 | MSCAST | P0 |  | Open
Q2 | PCC | Share the current PCC template, who prepares/approves it, how often it is revised, and whether it is at component or assembly level. | S-02, PC-03, P-09 | MSCAST | P0 |  | Open
Q3 | Project MIS | Share the 'New Project MIS' template and the monthly project cost MIS format. | PC-13, A-13 | MSCAST | P0 |  | Open
Q4 | BRM | Share the Billing Routing Memo format, approvers and payment release rules. A director certifies today: confirm that is MSCAST's intent. List the suppliers to mark *Exempt from BRM certification*. | P-08, A-05 | MSCAST | P0 |  | Open
Q5 | MDM / DI / Annexure-I | Share sample Material Dispatch Memo, Delivery Instruction and Annexure-I. | P-11, PC-04, P-12 | MSCAST | P0 |  | Open
Q6 | Biometric access control | Device make/model and count; network; should the ERP only read punches or also control door lock/unlock? | M-03 | MSCAST | P0 |  | Open
Q7 | Daily SMS | Recipients; is WhatsApp/Google Chat/email acceptable instead of SMS? Is DLT registration done? | AC-05 | MSCAST | P0 |  | Open
Q8 | Customer-owned assets | What are these assets? How are they recorded today? | AC-13 | MSCAST | P0 |  | Open
Q9 | GST on closing inventory | What report/working is expected? | AC-18 | CA | P0 |  | Open
Q10 | Accounting standards | CA to confirm AS vs Ind AS and SMC/small-company status; is a cash flow statement needed? | AC-07, A-14 | CA | P0 |  | Open
Q11 | WIP valuation | How is project WIP valued in Tally today? | AC-17 | CA | P0 |  | Open
Q12 | Payroll | Headcount under PF/ESI; current payroll provider; gratuity valuation method. | M-01, AC-23, AC-11 | MSCAST + CA | P0 |  | Open
Q13 | 8-year undertaking | Is an open-source + archival/backup policy acceptable in place of a vendor undertaking? | AC-06 | MSCAST | P0 |  | Open
Q14 | Additional claims | How are claims agreed and billed? | PR-07 | MSCAST | P1 |  | Open
Q15 | Spares Dept | Separate team? Spares from stock or order-based? Price lists? | PR-09 | MSCAST | P1 |  | Open
Q16 | Foreign travel / exports | Frequency, currencies, export orders? | A-12 | MSCAST | P1 |  | Open
Q17 | Equipment-wise man-hours | Which list defines 'equipment'? | E-06 | MSCAST | P0 |  | Open
Q18 | Flowchart order | Are long-lead bought-outs ordered before design is complete? | E-04, P-04 | MSCAST | P0 |  | Open
Q19 | Share register | Keep shareholder/share transfer records in the ERP, or with the company secretary? | AC-08 | MSCAST | P4 |  | Open
Q20 | Self-approval on the PCC and the kick-off | A director can prepare a PCC, or verify a customer PO, and then approve it alone (build check T6e). Confirm this is intended, or move preparation to staff. | S-02, PC-01 | MSCAST | Before go-live |  | Open
Q21 | Self-certification on supplier bills | A director can create a BRM, certify it and mark it paid, alone (build check T6g). This step releases money to an outside party. Confirm this is intended, or remove Projects Manager from the director accounts so that only Purchase can prepare a BRM. | P-08, PC-06, A-05 | MSCAST | Before go-live |  | Open