Table of Contents

# MSCAST ERP: Options Assessment & Phased Build Plan

Version: 1.1 (updated with MSCAST’s final requirement document) · Date: 16 Sep 2026 · Prepared for: Sanjay · Status: Recommendation, partly superseded by events. Written 16 September 2026, before the POC was built.

Read this first (added 20 September 2026). Sections 1–4, 8 and 11 — the platform decision, the alternatives assessment, the costing and the risk register — stand as written and are the reason this document exists. Sections 5, 6, 7, 9 and 10 have been overtaken by the build and should not be read as a description of what exists. Three differences matter:

- The AI layer was built differently. This document plans it on Gemini via Vertex AI in asia-south1, with a Google Cloud project and a per-token budget (decision D5). What was actually built runs on a local model router: a 16-rule exception sweep at 06:00 and an AI-written morning note at 08:35, at no per-document cost and with no cloud project. D5 is answered, not open.

- The app, the repository and the fixtures already exist. Section 6 lists them as P0 work to be done. mscast_erp is an installable app carrying every doctype, report, print format, workflow and control, with exported fixtures, at tagged release v0.9.0.

- The delivered BRM control is weaker than section 6 intends. That section assigns BRM certification to Procurement. In the built system a director can create a BRM, certify it and mark it paid alone. Purchase orders do require two people. This is open with MSCAST as Q21 in the traceability matrix.

For the current state of the system, read Requirements Traceability v1.7 and the POC README, not this document.

Decisions D1–D7 in §10 were open when this was written; D4 and D5 have since been answered by what was built.

Inputs: MSCAST “ERP_Requirement_Final” (PDF, 15 pages, incl. Accounts POV) — mapped line by line in the Requirements Traceability Matrix (97 requirements); ERPens “Revised Proposal – Mscast” (PDF); public research on MSCAST (see the MSCAST Knowledge Base); GitHub and web research on open-source ERPs, Frappe apps, alternative strategies and Gemini automation (see Research Appendix).

Assumptions confirmed by Sanjay on 16 Sep 2026: - Up to 10 ERP users. - Today’s tools are Tally Prime, Excel/Google Sheets, and paper/WhatsApp. - Delivery will be a phased self-build. - This is a greenfield project: it does not reuse any existing server or software stack. The only existing assets are the domain and Google Workspace.

## 1. Executive summary

What changed in v1.1. MSCAST’s final requirement document was mapped into 97 traceable requirements. - Coverage: about half are standard ERPNext v16 / India Compliance / Frappe HR features, a quarter are configuration, and 22 need custom work. One (biometric access control) is an integration; 3 need clarification or sit with the CA. - Gap in the ERPens proposal: by my reading, 31 requirements are not in it and 18 only partly. The biggest gaps are the PCC cost sheet, the Billing Routing Memo, the audit-trail and auditor login, MSME payables, biometric attendance, the daily management summary, project WIP valuation, and customer-owned assets. - Recommendation unchanged: ERPNext v16. - Timeline: extended by about 5 weeks, to Jul 2027. - Two new decisions: D6 (WIP valuation method) and D7 (daily-summary channel). - Payroll: PF/ESI/PT/TDS payroll is confirmed in scope.

- The ERPens proposal already is open source. It is ERPNext (GPL-3, 38.6k GitHub stars, v16.35.0 released 15 Sep 2026). The ₹3.6 L + GST buys configuration and customisation, not software. So there is no hidden open-source product to “switch to”. The real choice is who builds it, on which version, with which scope, and who owns the code.

- After checking ~25 alternatives, ERPNext v16 is still the best core system for MSCAST.

  - Alternatives checked: Odoo CE/EE + OCA, Dolibarr, iDempiere, OFBiz, Tryton, Axelor, metasfresh, AureusERP, Carbon, qcadoo; composable stacks (InvenTree + OpenProject + Mayan EDMS + Tally); low-code tools (AppSheet, NocoDB, Appsmith, Budibase); a custom Next.js build; SaaS (Zoho One, SAP B1).

  - Why ERPNext wins: it is the only fully open-source option covering all of these, without per-user licences:

    - India GST

    - e-way bill and e-invoice

    - GSTR-1/2B reconciliation

    - TDS

    - Indian payroll

  - Why it fits MSCAST: it already handles most of the engineer-to-order (ETO) project, procurement, subcontracting and quality flows MSCAST needs.

  - Runners-up:

    - Odoo Enterprise: full-featured but a recurring subscription (≈₹1,150 per user per month on the Custom plan, secondary source).

    - Zoho One: weak for ETO work.

    - Tally + InvenTree + OpenProject: cheap, but leaves data in separate silos.

- Roughly half of the proposal’s “custom development” line items are standard ERPNext v16 configuration. Examples: free-issue material, supplier scorecard, inspection templates, man-hour timesheets, approval workflows, bought-out tracking. The genuinely custom items are:

  - drawing register with revision control

  - engineering change requests and notices (ECR/ECN)

  - techno-commercial (technical + price) bid comparison

  - retention money

  - completion certificates

  - dispatch memo and dispatch schedule

  - bank guarantee (BG) and liquidated damages (LD) registers

  - inspection plan

- Most of these can be built with ERPNext’s no-code tools (custom forms and fields, workflows, print formats), packaged in a custom app.

- Recommended plan: a phased self-build on ERPNext v16, rolled out in six staggered phases over about 10 months (Oct 2026 – Jul 2027).

  - Operations go live first: engineering, projects, procurement, stock, dispatch.

  - Accounts move from Tally at the start of the financial year on 1 Apr 2027, a clean cut-over.

  - A parallel track adds Gemini-based automation step by step.

- Gemini automation is feasible and cheap, if designed as “AI drafts, humans approve”.

  - Stack: Google Apps Script or n8n, plus Gemini on Vertex AI in the Mumbai region (asia-south1), plus the ERPNext REST API.

  - First wins:

    - daily project/dispatch digest

    - Gmail/IndiaMART enquiry → Lead

    - supplier quotation PDF → Supplier Quotation draft with a techno-commercial summary

    - purchase invoice → draft with GST checks done in code, not by the AI

  - Model cost: estimated at about US$0.02 per document.

- Indicative 3-year cash cost:

  - Self-build: ≈₹2.5–4.5 L, plus Sanjay’s time.

  - ERPens: ≈₹7.8 L without their support plan, ≈₹12.5–14 L with it.

  - See §8. Every figure is labelled as an estimate or a verified price.

## 2. MSCAST in brief (from the Knowledge Base and the final requirement document)

Confirmed by MSCAST’s requirement document: - Business: engineering consultancy for the steel industry — design & drawing, consultancy, spares supply, equipment supply. - Manufacturing is outsourced. - Departments: Sales, Projects (with a project coordinator in Accounts), Engineering, Procurement, Accounts & Finance, Erection & Commissioning, Spares. - Key internal documents: - PCC (Purchase Cost Calculation) sheet - MDF (Material Data File / material list) - bought-out list - techno-commercial comparison - MDM (Material Dispatch Memo) with Annexure-I free-issue list - Delivery Instruction to suppliers, who ship direct to customer site - BRM (Billing Routing Memo) certifying supplier bills - PBG - proforma and retention supplementary invoices - commissioning / preliminary / final certificates - Accounts today: Tally, with a monthly project-cost MIS, BS, P&L and cash flow. - Accounts wants: - MCA audit trail with auditor login - alerts - a daily SMS summary to COO/CFO - 8-year record retention - Schedule III-style registers: MSME payables, fixed assets and CWIP, inventory and WIP, GSTR reconciliations, payroll reconciliation

From public research (to be confirmed in discovery):

- Legal and size: MSCAST Engineering Pvt Ltd, Pune (CIN U74900PN2010PTC137644, incorporated 29 Oct 2010, GSTIN 27AAGCM8444B1ZI). Up to 10 people. Declared turnover ₹1–2 Cr; GST turnover band ₹1.5–5 Cr.

- Offer:

  - Machines: continuous casting machines (CCMs) and CCM equipment for steel billets, aluminium billet casting machines, pouring casting machines, conveyors.

  - Engineering services: layouts, P&IDs, hydraulic circuits, erection supervision.

- Business model (inferred): a design-led engineer-to-order project business, probably outsourcing fabrication (job work).

  - Few, large orders (market prices ₹11 L – ₹2 Cr per machine).

  - Deep multi-level BOMs, many bought-out items.

  - Dispatch in lots, erection and commissioning, retention, bank guarantees.

- Online presence is minimal: two free IndiaMART listings, one TradeIndia listing, a placeholder website. There is a separate opportunity for digital lead generation.

What this means for the ERP: it must be project-centric (Sales Order = Project = cost centre). The key reports are project P&L (estimate vs actual), cash-flow forecast, and exposure to BGs, retention and LD. Transaction volume is low, so a small server is enough.

## 3. What the ERPens proposal really contains

| Proposal item | What it really is in ERPNext v16 | Classification |
| --- | --- | --- |
| CRM, Sales, Procurement, Inventory, Accounts, GST/TDS, Projects, HR/Payroll, Assets, roles, workflows | Standard modules + India Compliance app + Frappe HR | Configuration |
| Drawing upload & revision control | Nothing built in; a custom “Drawing” form with revision history and Draft → Released → Superseded workflow | Custom (mostly no-code) |
| Engineering documentation forms (“MDF”) | Custom forms and print formats (the meaning of “MDF” is still unknown) | Custom (no-code) |
| Bought-out item tracking | Item groups, Material Request from BOM, Procurement Tracker and Project-wise Stock Tracking reports | Configuration |
| Engineering approvals | Workflow | Configuration |
| Activity & man-hour tracking, engineering cost allocation | Timesheet, Activity Type/Cost → Project costing | Configuration |
| Project kick-off workflow | Project Template + Workflow | Configuration |
| Dispatch schedule | Delivery dates on Sales Order lines + custom report | Light custom |
| Completion certificate | New form + print format | Custom (no-code) |
| Retention amount tracking | Not in ERPNext or India Compliance; payment terms + custom fields + report (automatic retention ledger entries need code) | Custom |
| Supplier coordination, project-wise docs | Supplier portal, comments, assignments, Google Drive attachments | Configuration |
| Techno-commercial comparison | The built-in “Supplier Quotation Comparison” report compares price only; technical scoring must be added | Custom (light) |
| Material Dispatch Memo, delivery instructions | Delivery Note / Shipment + custom fields + print formats | Light custom |
| Free-issue material | Subcontracting Order “Supplied Items”, Customer Provided Items; India Compliance handles job-work GST challans | Configuration |
| Inspection planning | Quality Inspection Templates and Quality Procedures exist; an inspection plan/calendar is custom | Partly custom |
| Supplier performance | Supplier Scorecard | Configuration |

Missing from the proposal and required by MSCAST’s own document (see RTM, “In ERPens proposal” = No): - PCC sheet and PO-vs-PCC control - Billing Routing Memo - project MIS template and closure reports - SO↔PO↔invoice tracker - proforma invoice - additional claims - spares handover - MCA audit trail with auditor login - incomplete-data alerts - daily COO/CFO summary - 8-year retention and India data residency - MSME payables - gratuity, deferred tax and customer-owned (Tata Motors) assets - CWIP - project WIP valuation - biometric access-control attendance - cheque printing - prior-period and penalty accounts - warranty claims

Also missing (from business analysis): - bank guarantee and LC register with expiry alerts - liquidated damages tracking - milestone billing / payment schedules - cost-estimation sheet per machine family - engineering change requests and notices (ECR/ECN) - partial BOM release - e-way bill scope and India Compliance API credits - export documents and multi-currency - warranty, spares and service visits - data-migration volumes - ERPNext version (must be v16) - code ownership: a custom app in MSCAST’s own Git repository - handover and exit terms

Commercial observations: - AWS at ₹10k/month is high for ≤10 users. A managed Frappe Cloud Mumbai site or a small India VPS costs roughly half. - The 12–14 week “big bang” rollout gives the whole business one go-live. - The proposal says nothing about accounting cut-over timing against the financial year.

## 4. Options assessed (summary; details in the Research Appendix)

Scores are 1–5 (higher is better; for cost, higher = cheaper; for lock-in, higher = less lock-in).

| Strategy | India compliance | ETO fit | Cost | Time-to-value | Maintainability | Lock-in | Google Workspace fit | AI readiness | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ERPNext v16 + India Compliance (recommended) | 5 | 4 | 4 | 4 | 3 | 5 | 3 | 3 | 31 |
| Odoo 19 Enterprise (Custom plan) | 5 | 4 | 2 | 4 | 4 | 2 | 3 | 4 | 28 |
| Zoho One / Zoho apps (SaaS) | 5 | 2 | 3 | 5 | 5 | 1 | 3 | 4 | 28 |
| Low-code (AppSheet/NocoDB) + Tally | 2 | 3 | 4 | 4 | 2 | 3 | 5 | 3 | 26 |
| Odoo 19 Community + OCA | 3 | 4 | 3 | 3 | 2 | 4 | 3 | 2 | 24 |
| Best-of-breed OSS (InvenTree + OpenProject + Mayan) + Tally | 4 | 4 | 3 | 2 | 2 | 4 | 2 | 3 | 24 |
| Custom build (e.g. Next.js/Postgres) | 1 | 5 | 1 | 1 | 2 | 3 | 4 | 5 | 22 |
| SAP Business One | 5 | 3 | 1 | 3 | 4 | 1 | 2 | 3 | 22 |
| Carbon (crbnos) | 1 | 3 | 3 | 2 | 2 | 3 | 2 | 4 | 20 |
| Dolibarr / Tryton / iDempiere / Axelor / metasfresh / OFBiz | 1–2 | 2–4 | 3–4 | 2 | 2 | 4 | 1–2 | 1–2 | ≤20 |

Why the others fell short: - Odoo Community: GSTR filing (l10n_in_reports), Indian payroll, PLM, Quality, and full accounting reports are Enterprise-only. OCA l10n-india is empty. - Carbon: its licence restricts internal production use unless changes are open-sourced; no GST support. - Custom build: rebuilds what ERPNext already solves, and carries GST, payroll and audit-trail compliance risk. - Tally-centred stacks: no single project P&L across systems.

Compliance facts that shaped the choice: - Since 1 Apr 2023, every Pvt Ltd company must keep books in software with an audit trail (edit log) that cannot be switched off. This rules out spreadsheets and low-code tools for accounting. - E-invoicing is mandatory above ₹5 Cr aggregate annual turnover (AATO). MSCAST is near that band; confirm with the CA. - E-way bills apply to machine dispatches.

## 5. Target solution (greenfield)

Google Workspace (existing)
   Gmail · Calendar · Shared Drives · Chat · Meet · Gemini in Workspace
        │ Google Sign-In   │ drawings/docs      │ alerts / digests
        ▼                  ▼                    ▲
 ┌───────────────────────────────────────────────────────────┐
 │  erp.<mscast-domain>  — ERPNext v16 (Frappe Cloud Mumbai  │
 │  or India VPS)                                            │
 │   • ERPNext core  • India Compliance  • Frappe HR         │
 │   • mscast_erp (custom app, MSCAST-owned private Git repo)│
 │   • offsite_backups → Google Drive / S3                   │
 │   • Staging site (UAT) + Production site                  │
 └───────────────▲──────────────────────────────▲────────────┘
                 │ REST API (draft-only user)   │ Webhooks (HMAC)
        ┌────────┴──────────────────────────────┴───────┐
        │  Automation layer: Apps Script (start) → n8n  │
        │  Gemini on Vertex AI (asia-south1, Mumbai)    │
        └───────────────────────────────────────────────┘
   Tally Prime: stays the books of account until 31 Mar 2027,
   then read-only for FY 2026-27 audit.

| Layer | Recommendation | Why / notes |
| --- | --- | --- |
| ERP core | ERPNext v16 (not v15) | v16 is current; frappe/india-payroll works only on v16 |
| India compliance | India Compliance (resilient-tech, GPL-3, v16.9.0) | Covers GST, e-way bill, e-invoice, GSTR-1 (books vs filed reconciliation), 2A/2B purchase reconciliation, MCA audit trail (cannot be disabled once enabled; switch on at site creation) and Schedule III Balance Sheet/P&L templates. API calls use paid credits (500 free trial). Get a quote. |
| HR | Frappe HR (v16.18.1) for employees, leave, attendance, site expense claims | Payroll decision is D3 |
| Custom app | mscast_erp, private GitHub repo owned by MSCAST | All forms, custom fields, workflows and print formats exported as fixtures, so they are version-controlled and portable |
| Hosting (D1) | Must be in India: Companies (Accounts) Rules 2014, Rule 3(5), as amended 2022, requires daily backups of electronic books on servers physically located in India. Option A (recommended): Frappe Cloud, Mumbai region (server and offsite backups in ap-south-1). Site plans run $25–38/month (₹2,050–3,075) for Standard/Professional; custom apps need a private bench group (from $25/month). Expect ≈$50–65/month (≈₹4–5.5k); confirm at sign-up. Managed upgrades and backups. Option B: self-managed India VPS (e.g. DigitalOcean Bangalore; General Purpose 2 vCPU/8 GB is $63/month) running frappe_docker, plus a small staging droplet | Option A minimises ops work for a remote, one-person build team. You can move later: ERPNext is GPL and backups restore anywhere |
| Identity | Google Sign-In (built-in Social Login Key), restricted to the company domain | One login; offboarding happens in Workspace |
| Documents | Drawings and project files in a Shared Drive per project; ERPNext Drawing Register holds drawing number, revision, status, approval and Drive link | Uses Workspace storage, keeps ERP storage small, familiar to engineers |
| Email / calendar | Gmail email account in ERPNext; Google Calendar sync | Built-in |
| Reporting | ERPNext reports and dashboards; Frappe Insights later if needed |  |
| Automation / AI | Apps Script + Vertex AI to start (no new server); n8n in Docker when there are more than ~5 flows | See §7 |
| Mobile / site | ERPNext responsive web + Frappe HR mobile (attendance, expenses) |  |

## 6. Phased, staggered roadmap

Principles: - Each phase goes live on its own and is used for real before the next starts. - Tally stays the book of record until the year-end cut-over. - Every phase ends at a go/no-go gate with named MSCAST users signing off UAT on staging.

| Phase | Window (indicative) | Goes live for | Gate |
| --- | --- | --- | --- |
| P0 Discovery & foundations | 21 Sep – 16 Oct 2026 (4 wks) | Nobody yet | G0: scope, hosting, CA alignment |
| P1 Sales, PCC, projects & engineering core | 19 Oct – 4 Dec 2026 (7 wks) | Sales, projects, engineering | G1 |
| P2 Procurement, PCC control, BRM, stock, subcontracting, quality | 7 Dec 2026 – 29 Jan 2027 (8 wks incl. holidays) | Procurement, stores, QC | G2 (incl. D6 WIP method) |
| P3 MDM/DI dispatch, commercial controls + accounts dry-run | 1 Feb – 26 Mar 2027 (8 wks) | Project coordinator, procurement, accounts (trial) | G3: accounts cut-over go/no-go |
| P4 Accounts, GST, assets & MIS go-live | 1 Apr – 28 May 2027 (8 wks) | Accounts / CA / auditor / management | G4 |
| P5 HR, payroll, biometric attendance, after-sales | 1 Jun – 30 Jul 2027 (9 wks, 2 parallel payroll cycles) | All staff | G5: project close-out |
| AI track A1–A7 | Nov 2026 → mid 2027, in parallel | See §7 | Each flow has its own pilot gate |

### P0: Discovery & foundations (3–4 weeks)

- Discovery workshop with MSCAST. Use the 15-question agenda in KB 00-index.md: machine families, standard designs, BOM depth, in-house vs outsourced work, commercial terms (advance, retention, BG, LD), lead sources, what “MDF” means, data to migrate.

- Process maps (as-is → to-be) for: enquiry → quotation → order → engineering → procurement → job work → inspection → dispatch → erection → retention release.

- CA / tax consultant session:

  - Is e-invoicing applicable (AATO)?

  - Which HSN/SAC codes apply to complete machines vs services?

  - Job-work ITC-04 filing.

  - Accepting a Tally → ERPNext cut-over on 1 Apr 2027 (D2).

  - Audit-trail requirements.

- Collect MSCAST’s working formats:

  - PCC sheet

  - Project MIS template

  - BRM

  - MDM

  - Delivery Instruction

  - Annexure-I

  - certificates

  - claims

  - proforma and supplementary invoices

- Get answers to the 19 open questions in the RTM “Open Questions” sheet, e.g.:

  - “Finance Scaling Management”

  - biometric device model

  - Tata Motors assets

  - GST on closing inventory

  - WIP method

  - AS vs Ind AS

- CA session additions:

  - WIP valuation method (D6)

  - SMC / small-company status and cash flow statement

  - gratuity valuation method

  - MSME disclosures

  - acceptance of the 8-year archival policy instead of a vendor undertaking

- Foundations:

  - Decide hosting (D1, India-located) and provision production + staging sites. Enable the India Compliance audit trail at site creation.

  - Set up erp.<domain> DNS and SSL.

  - Configure Google Sign-In and a Shared Drive structure.

  - Create the private Git repo and scaffold mscast_erp. Done — but note where: the repository is github.com/cb1-tech/mscast, not MSCAST’s own. §3 of this document gives code ownership in MSCAST’s repository as a reason for preferring a self-build over the ERPens proposal, so on that test the objective is not yet met. Transferring or mirroring the repository to MSCAST is a decision worth taking deliberately rather than by default.

  - Define naming conventions (projects, items <Project>-<Assy>-<DrgNo>-<Rev>, drawings).

  - Set up user roles.

- Master-data templates: customers, suppliers (capability tags, approved makes), item groups (machines, assemblies, fabricated, bought-outs by category, raw material, spares, services), UOMs (Nos, Set, Kg, m, Manhour, Manday, Lot).

- Exit criteria (G0): signed scope and backlog; hosting live; CA agrees the accounting approach; data owners named.

### P1: Sales, PCC, projects & engineering core (≈7 weeks)

- PCC (Purchase Cost Calculation) sheet:

  - A custom form per Sales Order/Project: component-wise estimated cost, make and supplier category.

  - Revisions and approval.

  - It is the baseline for procurement control and the project MIS.

- Kick-off handover:

  - A checklist with mandatory PCC, signed technical specs, sales MOMs and contract/scope.

  - Purchase-order checks against the agreed terms.

  - Notifications to Engineering, Projects, Procurement and Finance.

  - Project code naming series.

- Client schedules: project execution, delivery and billing schedules as print formats; periodic overall project status report to the client.

- MDF: Material Data File / material list per project/assembly from final drawings, plus the bought-out list, generating Material Requests.

- Timesheets: man-hours captured equipment-wise and project-wise.

- CRM: Lead → Opportunity → Quotation with versions. Lead source tags: IndiaMART, TradeIndia, referral, exhibition. Technical questionnaire (child table), cost-estimate sheet per machine family.

- Sales Order → Project created from a template with a kick-off workflow and milestones: GA approval, BOM release, dispatch lots, erection, commissioning.

- Timesheets: activity types (layout, detail design, hydraulics, P&ID, vendor visit, site) → man-hour cost rolls up to the project.

- Custom:

  - Drawing Register (revision table, customer-approval status, transmittals, superseded control, Drive link)

  - ECR/ECN approval workflow

  - engineering documentation forms (“MDF”)

- Engineering BOMs per project (multi-level, partial release of long-lead items); template BOMs for standard assemblies.

- Migration: open projects, customers, key suppliers, item catalogue (bought-outs first).

- Exit (G1): all live projects in ERPNext with tasks, drawings and hours logged for 2+ weeks; project status meeting runs from ERPNext, not Excel.

### P2: Procurement, PCC control, BRM, stock, subcontracting & quality (≈8 weeks)

- PO vs PCC control: variance report, with approval required when a PO exceeds the PCC. PCC status updates.

- Billing Routing Memo (BRM): Procurement certifies the supplier bill/proforma/internal memo against the PO. In P2–P3 it is a register (Tally still books); from P4 it gates Payment Entry.

- Drawing/MDF transmittal to equipment manufacturers.

- Vendor free-issue stock declarations project-wise.

- Supplier MSME/Udyam fields captured.

- Major-value PO alerts to management (see D7).

- D6 decided with the CA: project WIP valuation method (Work Order + WIP warehouse vs Project WIP account + JV), because it affects warehouse and account setup.

- Purchasing: Material Request from BOM → RFQ (supplier portal / email) → Supplier Quotation → techno-commercial comparison (custom technical scoring + built-in price comparison; custom print) → approval workflow → PO.

- Stock: purchase receipts, stock entries, project-wise stock. Perpetual inventory stays off until P4, so there are no accounting postings while Tally is still the book of record.

- Subcontracting / job work: Subcontracting Order with supplied (free-issue) items, vendor-wise balance, subcontracting receipt, GST job-work challans (India Compliance) → ITC-04 data.

- Quality:

  - Quality Inspection Templates per item group

  - Inspection plan (custom: stage/final/third-party inspection calendar per project and vendor)

  - pre-dispatch inspection as a mandatory gate

- Supplier Scorecard: on-time delivery, rejection %.

- Exit (G2): every PO for new projects raised in ERPNext; free-issue balances reconcile with vendors; inspection records attached.

### P3: MDM/DI dispatch & commercial controls, plus accounts dry-run (≈8 weeks)

- Material Dispatch Memo → Delivery Instruction to supplier (direct-to-site dispatch, transport arrangement), with Annexure-I free-issue list.

- Billing & despatch schedule updated with consignor, transporter, LR no./date and invoice no./date.

- Proforma invoice for advances and scheduled supply.

- Additional client claims register.

- Commissioning / Preliminary / Final certificates.

- PBG register.

- Erection & commissioning: site tasks, timesheets and expense claims.

- Dispatch: contractual delivery schedule vs actual; Material Dispatch Memo, packing list, Delivery Note per lot (supports ship-from-vendor), e-way bill through India Compliance.

- Commercial: payment-terms templates (advance / against dispatch / commissioning), milestone billing plan, retention tracker, BG/LC register with expiry alerts, LD exposure report, completion certificate form and print.

- Accounts dry-run (Feb–Mar 2027):

  - Chart of accounts, tax templates and TDS categories set up on staging.

  - Load test opening balances from Tally (e.g. 31 Dec 2026).

  - Run one month of invoices in parallel on staging.

  - CA reviews GSTR-1 and the 2B reconciliation outputs.

  - Load the fixed-asset register (Companies Act and Income Tax finance books, CWIP, intangibles, customer-owned asset register) and MSME supplier data for the opening balances.

  - Configure the Auditor role (read-only, held by the external CA) and the MSCAST Director role (approving). Corrected 20 Sep 2026: an earlier version of this line described MSCAST Director as read-only. It is the opposite — it is the approving role, carrying PCC approval, purchase order approval, BRM certification and kick-off approval.

- Exit (G3): dispatches and e-way bills from ERPNext; CA signs off the accounts dry-run → go/no-go for 1 Apr 2027.

### P4: Accounts & GST go-live (from 1 Apr 2027)

- Opening balances as of 31 Mar 2027: provisional on day 1, finalised after Tally year-end close. Covers customer/supplier open items, retention receivables, advances, stock, assets, bank.

- Live transactions: sales invoices (e-invoice if applicable), purchase invoices, payments, bank reconciliation, TDS, GSTR-1 export, 2A/2B reconciliation; perpetual inventory switched on.

- Project P&L (estimate vs actual) and cash-flow forecast go live.

- Monthly MIS of project costs, PCC vs actual, and SO↔PO↔invoice tracker.

- Project completion accounting closure report.

- BRM-gated project payments.

- Cheque printing, petty cash and supplementary (retention) invoices.

- Schedule III Balance Sheet/P&L templates; expense last-year comparison and ratio to sales; TDS on expenses.

- Separate accounts for prior-period items and fines/penalties.

- MSME 45-day dues report (Form I, Schedule III, s.43B(h)).

- Fixed assets live with depreciation.

- Daily management summary (D7) and incomplete-data alerts.

- Auditor login.

- 8-year archival SOP: yearly dumps plus year-end exports.

- Tally becomes read-only for the FY 2026-27 audit. Keep its TSS subscription until the audit closes.

- Fallback if D2 = keep Tally: ERPNext stays the operations system; monthly voucher export to Tally via XML/JSON integration. Accept that project P&L will be partial.

- Exit (G4): first monthly close and GST return filed from ERPNext.

### P5: HR, payroll, biometric attendance, after-sales (≈9 weeks)

- HR: employees, attendance (mobile), leave, expense claims for site travel booked to projects.

- Payroll (D3, revised): PF, ESI, PT and TDS payroll with salary slips is required.

  - Run Frappe HR + india-payroll in parallel with the current payroll for June and July 2027, then go live.

  - Before go-live, verify the Maharashtra Professional Tax women-exemption fix (₹25,000 threshold) is in the v16 release; the v16.0.4 code still uses ₹10,000.

- Payroll reconciliation: Salary Register and PF/ESI/PT/TDS registers.

- Gratuity: payouts in Frappe HR; the liability valuation is an external/rational method booked by journal entry.

- Biometric access-control attendance:

  - Device punches go to Employee Checkin, then Shift auto-attendance.

  - ZKTeco/eSSL via the LAN sync tool or ADMS push; Matrix COSEC via a small connector.

  - Door locking stays in the access-control system.

- Assets: (register moved to P4) tools and instruments with calibration.

- After-sales: project closure handover to the Spares Dept (installed-machine record), serial number per machine/strand, warranty claims, maintenance visits, spares sales orders, AMC.

- Close-out: admin runbook, backup restore test, user guide (short videos), handover.

### Staggering and parallel-run rules

- Only one department cuts over at a time; the previous phase must be stable for ≥2 weeks.

- Everything is built and tested on staging first. Production changes ship via the Git repo, never by editing production directly.

- For each phase, name one key user at MSCAST who owns UAT and trains colleagues.

- Remote-delivery note: MSCAST is in Pune and the build lead works remotely. Budget for (a) scheduled video UAT sessions and (b) optionally a local Pune ERPNext freelancer or partner for on-site training and the P4 accounts cut-over.

## 7. Gemini automation track (parallel)

Design rules: - A dedicated “AI Integration” ERPNext user may create drafts only, never submit (enforced by role). - JSON-schema output from Gemini; totals, taxes and GSTINs re-checked in code. - Source file always attached; low-confidence results go to “Needs Review”. - No HR/payroll data sent to AI. - Paid API only: Vertex AI in asia-south1 for India data residency (currently only certain models, e.g. Gemini 3.5 Flash / 2.5 Flash, are processed in India; check the model list at build time). - Google Cloud budget alerts; every AI action logged.

| # | Flow | Build on | Starts after | Value | Risk |
| --- | --- | --- | --- | --- | --- |
| A1 | Daily project & dispatch digest and COO/CFO summary: overdue tasks, drawings pending approval, POs over PCC, dispatches this week, BG expiries; from P4, major-value transactions and revenue/receipts vs purchases/expenses → Google Chat / WhatsApp / email (D7) | Apps Script (time trigger) → ERPNext REST → Gemini summary → Chat webhook | P1 (Nov 2026) | High visibility, zero data entry | Very low (read-only) |
| A2 | Enquiry → Lead: sales Gmail + IndiaMART/TradeIndia emails classified; company, country, machine type, billet size, capacity extracted → Lead draft, duplicate check | Apps Script Gmail trigger or Workspace Studio triage → REST | P1 (Dec 2026) | No lost enquiries; source analytics | Low |
| A3 | Supplier quotation PDF → Supplier Quotation draft + techno-commercial summary (rates, GST %, delivery, payment terms, validity, deviations from spec) posted to the RFQ | n8n (or Apps Script) → Gemini (PDF input) → match to RFQ items → REST | P2 (Jan–Feb 2027) | Big time saver for buyers | Medium: item mapping; human check |
| A4 | Supplier bill → BRM + Purchase Invoice draft with GSTIN checksum, supplier match, CGST/SGST vs IGST by state code, totals reconciliation (all in code) | n8n → Gemini → validation → REST (consider adapting open-source erpocr_integration) | P4 (Apr–May 2027) | Faster AP, fewer typos | Medium: finance review mandatory |
| A5 | Meeting notes → Tasks: Gemini in Meet notes/Doc → actions, owner, due date, project → Task drafts | Apps Script → Gemini → REST | P1+ (anytime) | Follow-through on customer/vendor meetings | Low |
| A6 | Ask-ERP: natural-language questions over ERP data, read-only, permission-aware | Frappe Assistant Core (MCP, AGPL) or frappe/mcp + Gemini CLI | P4 (mid 2027) | Owner self-service analytics | Medium: read-only role, logged |
| A7 | Drawing title block / BOM table → Item + BOM drafts (pilot) | Gemini on exported PDF/Excel BOMs; prefer CAD BOM exports | After P2, pilot only | Faster BOM creation | High for dense drawings; limit to title block + part list |

Workspace-native extras (no build): Gemini in Gmail/Docs/Meet (included in Workspace Business plans at different levels; check MSCAST’s edition) for drafting quotations and cover letters, and summarising customer spec documents.

Cost indication (estimate): ~US$0.02 per 5-page document on Gemini 3.5 Flash (Vertex regional). At MSCAST volumes (a few hundred documents a month) that is under ~US$10/month. Watch for “thinking-token” usage and price changes (some Flash models reprice on 1 Jan 2027).

## 8. Indicative 3-year cost comparison (cash, excl. internal time)

| Item | ERPens proposal | Self-build (recommended) | Basis |
| --- | --- | --- | --- |
| Implementation | ₹3.6 L + 18% GST ≈ ₹4.25 L | ₹0 cash (Sanjay’s time) + optional Pune freelancer for training/accounts cut-over ₹0.5–1.5 L (estimate) | Proposal; freelancer rate unverified |
| Hosting (36 months) | AWS ₹10k/month after month 1 ≈ ₹3.5 L (“may increase”) | Frappe Cloud Mumbai ≈ ₹4–5.5k/month ≈ ₹1.5–2.0 L (or VPS ≈ similar) | Frappe Cloud price page; confirm bench + site total at sign-up |
| Support | Optional ₹25k/month + GST (includes cloud, 20 dev-hrs) ≈ ₹10 L over ~33 months, replacing AWS line | Own; Frappe community; ad-hoc paid help as needed | Proposal |
| India Compliance API credits | Not mentioned | Needed for e-way bill/e-invoice/GSTIN checks: get quote (500 free credits) | Price not published |
| Gemini / Google Cloud | n/a | ₹0.1–0.4 L over 3 years (estimate, with buffer) | Published per-token prices |
| Tally | Not addressed | TSS until FY26-27 audit closes (~₹5–15k) | Tally price page |
| 3-year total | ≈₹7.8 L (no support) · ≈₹12.5–14 L (with support; excl./incl. GST) | ≈₹2.5–4.5 L + credits |  |

Hidden cost of self-build: time and key-person risk. After mapping MSCAST’s final requirements, custom and configuration work is estimated at ≈28 person-weeks (RTM Summary sheet). Adding standard setup, data migration, training and UAT gives ≈35–45 person-weeks spread over about 10 months, plus about 6–10 weeks for the AI track. Mitigations: Git repo, staging, runbook, documented fixtures, and the option to engage a Frappe partner for specific tasks.

## 9. Custom app backlog (mscast_erp)

Effort sizes: S ≤2 days · M 3–6 days · L 7–12 days. “No-code” means built with ERPNext’s settings screens (custom forms and fields, workflows, print formats, Server Scripts), exported into the app.

| # | Feature | Approach | Phase | Size |
| --- | --- | --- | --- | --- |
| 1 | Project template + kick-off workflow + milestones | Config | P1 | S |
| 2 | Quotation cost-estimate sheet per machine family | No-code form + child tables | P1 | M |
| 3 | Technical questionnaire on Opportunity | Custom fields/child table | P1 | S |
| 4 | Drawing Register with revisions, approvals, transmittals, Drive links | Custom form + workflow + Server Script | P1 | L |
| 5 | ECR/ECN with impact list (BOM/MR/PO) | Custom form + workflow; auto-replacement later (Python) | P1/P2 | M |
| 6 | Engineering doc forms (“MDF”) | Custom form + print format | P1 | S–M |
| 7 | Techno-commercial comparison (technical scoring + price) | Custom fields on Supplier Quotation + script report + print | P2 | M |
| 8 | Inspection plan / calendar | Custom form linked to PO/project + report | P2 | M |
| 9 | Free-issue material balance by vendor (ITC-04 support) | Standard subcontracting + report | P2 | S |
| 10 | Dispatch schedule vs contract + Material Dispatch Memo + packing list | Custom fields, form, print formats, report | P3 | M |
| 11 | Retention tracker (and optional retention receivable postings) | Payment terms + custom fields + report; postings in Python | P3/P4 | M |
| 12 | BG/LC register with expiry alerts; LD exposure report | Standard Bank Guarantee + notifications + report | P3 | S–M |
| 13 | Completion certificate | Custom form + print | P3 | S |
| 14 | Project P&L (estimate vs budget vs actual) and cash-flow forecast | Script/query reports, dashboard | P4 | M–L |
| 15 | Warranty / serial / service visit setup | Config | P5 | S |
| 16 | AI integration user, custom fields ai_generated/ai_confidence/ai_raw_json, webhooks | Config + small code | AI track | S |
| 17 | PCC sheet with revisions + PO-vs-PCC variance/approval | Custom form + script report + server script | P1/P2 | L + M |
| 18 | Billing Routing Memo (register → Payment Entry gate) | Custom form + workflow + server script | P2/P4 | M |
| 19 | Project MIS (MSCAST template) and project closure report; SO↔PO↔invoice tracker | Script reports | P1/P4 | M + M |
| 20 | Additional client claims; Commissioning/PAC/FAC certificates; proforma print | Custom forms + print formats | P3 | S |
| 21 | Equipment-wise man-hours | Custom field + report | P1 | S |
| 22 | MSME supplier fields + 45-day dues report | Custom fields + script report | P2/P4 | M |
| 23 | Auditor role (read-only) and MSCAST Director role (approving), plus Design User; incomplete-data alerts; archival SOP | Config | P0/P4 | S |
| 24 | Daily COO/CFO summary (email digest + WhatsApp/Chat or DLT SMS) | Config + small scheduled job | P4 | M |
| 25 | Project WIP valuation (per D6) | Config or small script | P3/P4 | M |
| 26 | Customer-owned (Tata Motors) asset register | Custom form | P4 | S |
| 27 | Biometric access-control attendance connector | Integration | P5 | M |

## 10. Decisions needed

| ID | Decision | Recommendation | Needed by |
| --- | --- | --- | --- |
| D1 | Hosting: Frappe Cloud Mumbai (managed) vs self-managed India VPS | Frappe Cloud (private bench) for P0–P5; revisit at 12 months | P0 (early Oct 2026) |
| D2 | Accounting: move from Tally on 1 Apr 2027 vs keep Tally permanently | Move on 1 Apr 2027, subject to CA dry-run sign-off (G3) | CA meeting in P0; final at G3 |
| D3 | Payroll: ERPNext india-payroll vs keep current provider (revised: PF/ESI/PT/TDS payroll is a stated requirement) | Move to india-payroll after 2 parallel cycles (Jun–Jul 2027), subject to PT bug check | P5 |
| D6 | Project WIP valuation method: Work Order + WIP warehouse vs Project WIP account + JV | Agree with CA; lighter JV method unless MSCAST needs stage-wise WIP | Gate G2 (Jan 2027) |
| D7 | Daily COO/CFO summary channel: SMS (TRAI DLT, ≤40 chars per variable) vs WhatsApp utility template vs Google Chat/email | Email digest + WhatsApp or Google Chat; optional one-line DLT SMS alert | P3 |
| D4 | ERPens: decline, renegotiate, or retain for specific tasks only | Decline the fixed-bid proposal; optionally keep a paid on-call Frappe expert (ERPens or a Pune partner) for the accounts cut-over | Now |
| D5 | Google Cloud project for Vertex AI under MSCAST Workspace (billing owner, budget cap) | Create in P1 with a ₹1–2k/month budget alert | Before A1 |

## 11. Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| Key-person dependency (one builder, remote) | Git, staging, fixtures, runbook; a named MSCAST key user per phase; optional partner retainer |
| Adoption at a ≤10-person firm used to WhatsApp and Excel | Operations-first phasing; mobile-friendly screens; daily digest (A1) makes ERP the place to look; stop parallel Excel after each gate |
| Accounting/GST errors at cut-over | Financial-year boundary, CA dry-run, Tally read-only fallback |
| India Compliance credit costs | Disable unneeded GSTIN validations; watch the usage report |
| Young apps (india-payroll, AI community apps) | Parallel runs; pin versions; prefer thin integrations |
| AI mistakes or prompt injection from external PDFs/emails | Draft-only role, code-side validation, no auto-submit, logging |
| Unclear requirements (“Finance Scaling Management”, “GST on closing inventory”, Tata Motors assets) | Open Questions sheet resolved at G0; unresolved items deferred, not guessed |
| Compliance expectations beyond ERP (Ind AS list, 8-year vendor undertaking) | CA confirms AS/SMC status; archival SOP + open-source licence in place of an undertaking |
| Biometric device incompatibility | Get the device model in P0; budget a connector or device replacement |
| Scope creep (e.g. export docs, full PLM) | Backlog with phase gates; changes go into the next phase |

## 12. Next 2 weeks

- Sanjay reviews this plan and the Requirements Traceability Matrix; decides D1, D4, D5 and sends the 19 open questions and the format request (PCC, MIS, BRM, MDM, DI, Annexure-I) to MSCAST.

- Book the MSCAST discovery workshop (2 × 2-hour video sessions) using the KB question list; also collect sample documents (quotation, PO, BOM/drawing list, dispatch memo, invoice, retention letter, BG).

- Book the CA session (D2, e-invoice applicability, HSN/SAC, ITC-04).

- Provision hosting (staging first), set up the domain and Google Sign-In, and create the Git repo.

- Prepare master-data Google Sheets templates for MSCAST to start filling.

### Key sources

- ERPNext: https://github.com/frappe/erpnext · India Compliance: https://github.com/resilient-tech/india-compliance · Frappe HR: https://github.com/frappe/hrms · India Payroll: https://github.com/frappe/india-payroll · Offsite backups: https://github.com/frappe/offsite_backups

- Frappe Cloud pricing (Mumbai region): https://frappe.io/cloud/sites · DigitalOcean pricing: https://www.digitalocean.com/pricing/droplets

- Odoo editions/pricing: https://www.odoo.com/page/editions · https://www.odoo.com/pricing · Odoo India docs: https://www.odoo.com/documentation/19.0/applications/finance/fiscal_localizations/india.html

- Retention money gap: https://discuss.frappe.io/t/retention-money/127161 · Item revisioning gap: https://discuss.frappe.io/t/item-revisioning/162669

- Gemini models/pricing: https://ai.google.dev/gemini-api/docs/models · https://ai.google.dev/gemini-api/docs/pricing · Vertex data residency: https://docs.cloud.google.com/gemini-enterprise-agent-platform/resources/data-residency

- Frappe webhooks/REST: https://docs.frappe.io/framework/user/en/guides/integration/webhooks · https://docs.frappe.io/framework/user/en/api/rest

- Audit trail rule: https://www.india-briefing.com/news/india-mandates-audit-trail-compliance-for-all-companies-explainer-key-obligations-34837.html/ · E-invoice threshold: https://www.gimbooks.com/blog/5-crore-e-invoice-turnover-rule-2026/

- MSCAST public profile: https://www.indiamart.com/mscast-engineering/ · https://www.zaubacorp.com/company/Mscast-Engineering-Private-Limited/U74900PN2010PTC137644

- Companies (Accounts) Rules audit trail & India backups: https://www.scconline.com/blog/post/2022/08/16/record-keeping-requirements-modified-vide-companies-accounts-fourth-amendment-rules-2022/ · ICAI audit trail guidance: https://cajournal.icai.org/article-details/audit-trail-requirements-responsibilities

- Ind AS applicability (Rule 4): https://ca2013.com/rule-4-companies-indian-accounting-standards-rules-2015/ · Companies (AS) Rules 2021 / SMC: https://taxguru.in/company-law/companies-accounting-standard-rules-2021.html

- Small company threshold (Dec 2025): https://www.scconline.com/blog/post/2025/12/02/mca-notified-expansion-threshold-limit-small-companies-2025-compliance-update-scctimes/ · MSME Form I: https://mmjc.in/change-in-form-msme-1-exhaustive-disclosure-framework/

- SMS DLT templates: https://msg91.com/help/dlt-registration-in-india/dlt-content-template-faqs · Biometric integration: https://docs.frappe.io/hr/integrating-frappe-hr-with-biometric-attendance-devices · Frappe Cloud backups: https://docs.frappe.io/cloud/sites/backups

- The full source lists are in the Research Appendix and the KB sources.md.